# Executive Summary

EmergentOS (EOS) is a modular, adaptive operating system designed to align product and engineering teams around customer outcomes—not just feature delivery. It replaces legacy planning models with a quarterly cadence that integrates strategic alignment, flow optimization, and continuous improvement. Core components include Marty Cagan’s Product Operating Model, OKRs, Team Topologies, Kanban, Lean Kata, CI/CD, DORA metrics, and value stream management using The Flow Framework—all reinforced by a culture of empirical learning and coaching-led governance.

EmergentOS empowers teams to make high-integrity commitments based on validated learning and evolving confidence, experiment safely, and deliver measurable impact. It is especially suited for organizations seeking speed, adaptability, and strategic clarity without sacrificing autonomy or sustainability.

The operating system explicitly rejects deterministic planning as a default, recognizing it as an anti-pattern in adaptive environments. Instead, it promotes empirical, outcome-driven delivery and validated discovery. Deterministic techniques may be used in low-uncertainty contexts, but only as optional tools—not foundational mechanisms.

“Rather than the domain of work being repetitive, knowable, and deterministic with known-unknowns (you know how to fix it if something goes wrong), unique product development is unknowable and emergent with unknown-unknowns instead. For something that has not been done before, you don’t know what you don’t know until you do something and get feedback.”

— Jonathan Smart, Sooner Safer Happier

# Who Is This For?

EmergentOS is designed for organizations operating in complex, fast-changing environments where adaptability, speed, and measurable impact matter more than rigid predictability. It is ideal for:

- Product and Engineering Leaders
Seeking to align strategy and delivery around customer outcomes, empower teams, and replace estimation-heavy planning with evidence-based decision-making.

- Cross-Functional Product Teams
Looking for autonomy, clarity, and practices that enable continuous discovery, iterative delivery, and sustainable flow.

- Enterprise Functions Beyond Engineering
Including Finance, HR, Operations, and Transformation teams that need adaptive planning, flow-based governance, and outcome-driven investment models.

- Executives and Change Agents
Driving transformation from output-focused delivery to outcome-focused strategy, and fostering a culture of learning, empowerment, and coaching-led leadership.

EmergentOS is not a prescriptive methodology. It is a modular, composable operating system for organizations that want to evolve continuously, experiment safely, and scale agility without sacrificing autonomy or wellbeing.

# Disclaimer

This document was generated with the assistance of Artificial Intelligence (AI). While every effort has been made to ensure accuracy, clarity, and relevance, AI-generated content may include assumptions, omissions, or interpretations that differ from human-authored work.

Consequences and Considerations:

Validation Required: Recommendations and practices described herein should be reviewed and validated by subject matter experts before implementation.

No Liability: The authors and AI provider accept no responsibility for decisions made solely based on this document.

Dynamic Context: AI-generated insights may not account for all organizational, regulatory, or contextual factors. Adaptation to your specific environment is essential.

# EmergentOS

Aligned, Empowered, Sustainable, Adaptive

In today’s fast-moving technology landscape—where speed, adaptability, and customer impact define success—organizations can no longer afford delivery models that prioritize predictability over responsiveness, outputs over outcomes, or estimates over evidence. Traditional waterfall methodology and process heavy ‘enterprise’ frameworks like SAFe®, built around centralized orchestration and estimation-reliant planning, often struggle to keep pace with the demands of modern product development.

EmergentOS (EOS) offers a strategic shift: a quarterly, outcome-focused delivery system that replaces legacy processes with a modular, empirically grounded operating model. It empowers cross-functional teams, accelerates flow, and drives measurable business impact. It is not a methodology—it is a composable, modular operating system for product and engineering organizations, built from proven techniques that reinforce one another to create strategic alignment, operational clarity, and continuous improvement.

Use EmergentOS to become:

- Aligned
Strategy and execution connected through outcomes.

- Empowered
Teams trusted to own outcomes and make decisions.

- Sustainable
Delivery at a resilient pace, enabling long-term impact.

- Adaptive
Evolving continuously through flow and learning.

While EOS offers a comprehensive set of practices, it is intentionally not prescriptive. It is designed as a modular, composable operating system—not a rigid methodology. Each component (e.g. OKRs, Lean Kata, Team Topologies, CI/CD) can be adopted independently and scaled based on team maturity and context. EOS provides principles and proven patterns, not mandates. It empowers teams to evolve their ways of working through experimentation, evidence, and coaching, ensuring that agility is achieved through adaptability—not adherence.

# Rationale & Strategic Importance

What Are You Optimizing For?

This is an important question to ask. Within your organization, what are you optimizing for? Are you optimizing for the fast flow of safe value with high levels of customer advocacy and colleague engagement? Or for role-based silos, where work is passed over the wall to the next role-based silo with little notion of end-to-end ownership? Are you optimizing for value and time to value, or pushing a “promise of a future solution” through endless gates and committees for years? Are you optimizing for fast learning and pivoting in order to maximise outcomes in the shortest possible time and with the least effort and risk? Or following a predetermined project plan with learning and risks back-loaded to the end with a large impact radius, big-bang implementation? Are you optimizing for everyone using their brains to run safe-to-learn experiments to continuously improve or for following orders?
— Jonathan Smart, Sooner Safer Happier

At its core, EmergentOS (EOS) is built to solve a fundamental problem: traditional scaled agile models often create the illusion of control through predictive scheduling, rigid planning increments, and dependency-heavy orchestration. While these models may offer short-term clarity, they frequently stifle innovation, slow down delivery, and disconnect teams from customer value.

Implementing EOS will reorient delivery around customer outcomes, not feature roadmaps. It empowers stream-aligned product teams to own their work, experiment rapidly, and improve continuously. It integrates Lean Value Trees and OKRs for strategic alignment, Team Topologies for scalable team interactions, Value Stream Management and Kanban for flow visualization, and Lean Kata for operational improvement. Engineering excellence is embedded through Continuous Integration (CI) and Continuous Delivery (CD), DORA and Flow metrics, and a culture of empirical learning.

By running on a quarterly cadence, EOS balances strategic planning with tactical agility—allowing teams to commit to meaningful goals while adapting to change.

# Beyond Engineering: Enterprise-Wide Applicability of EmergentOS

Although EmergentOS was designed to optimize product delivery, its modular architecture, outcome-driven planning, and flow-based governance make it highly applicable across the broader enterprise. Functions such as Finance, HR, Operations, Transformation, Risk, and Strategy can benefit from its principles and practices—especially in environments where adaptability, learning, and measurable impact are essential.

## Strategic Planning & Alignment

- Lean Value Trees (LVTs) and Strategic Outcome Mapping help any department translate high-level goals into measurable outcomes.

- OKRs provide clarity and focus, enabling teams to prioritize work that drives strategic value.

Applicable to: Strategy, Transformation, Finance, HR

## Adaptive Budgeting & Investment

- EmergentOS’s adaptive funding model replaces fixed annual budgets with quarterly, evidence-based investment decisions.

- Innovation accounting supports funding for discovery, experimentation, and continuous improvement.

Applicable to: Finance, Portfolio Management, Transformation Offices

## Flow-Based Governance & Visibility

- Portfolio Kanban visualizes initiative flow across departments, enabling leaders to coach through flow rather than control through timelines.

- Flow Metrics and telemetry provide real-time insight into progress and bottlenecks.

Applicable to: Executive Leadership, Shared Services

## Continuous Improvement & Capability Building

- Lean Kata and Flow Engineering can be used by any team to identify blockers, run experiments, and improve how work flows.

- Improvement work is tracked as OKRs and reviewed quarterly.

Applicable to: Operations, HR, Compliance, Customer Service

## Coaching-Led Governance & Leadership Development

- EmergentOS promotes developmental governance, where leaders act as coaches rather than controllers.

- Intent-Based Leadership and coaching rituals support psychological safety, autonomy, and growth.

Applicable to: HR, Leadership Development, Culture & Change Teams

## Organizational Design & Team Interaction

- Team Topologies principles help structure teams across the enterprise to reduce cognitive load and improve collaboration.

- Interaction modes (e.g. collaboration, X-as-a-service, facilitating) apply to both technical and non-technical teams.

Applicable to: Org Design, Transformation, HR, Shared Services

| Domain | EmergentOS Practices That Apply |
| --- | --- |
| Strategy & Planning | Lean Value Trees, OKRs, Strategic Outcome Mapping |
| Finance & Budgeting | Adaptive Funding, Innovation Accounting, Portfolio Kanban |
| HR & People Development | Coaching Culture, Team Topologies, Slowification |
| Transformation & Change | Quarterly Cadence, Lean Kata, Flow Engineering |
| Operations & Service | Flow Visualization, Continuous Improvement, Telemetry |
| Leadership & Governance | Coaching-led governance, Intent-Based Leadership, Portfolio Kanban |

## Summary

EmergentOS is not just a delivery system—it is a strategic operating model for adaptability. Its principles of outcome focus, flow optimization, continuous learning, and coaching-led governance are universally applicable. By extending EmergentOS beyond engineering, organizations can align every function around measurable impact, accelerate enterprise-wide learning, and build a culture of empowered, evidence-driven decision-making.

# Show Me the Money!

Traditional funding models are built for predictability and control in low-uncertainty environments. They assume that scope, effort, and value can be forecast accurately. In contrast, EmergentOS’s adaptive funding model is designed for high-uncertainty, fast-changing environments, where learning, experimentation, and customer impact are the true indicators of success.

## Adaptive Funding Model: Investing in Outcomes, Not Outputs

### 1. Strategic Framing via Lean Value Trees

- Funding begins with strategic themes and bets defined in Lean Value Trees (LVTs).

- Each bet is a hypothesis about where investment will drive measurable outcomes.

- Initiatives are prioritized based on expected value, not effort or scope.

“If we invest in X, we expect to see Y outcome, because Z.”

### 2. Metered Funding via Hypothesis Validation

- Initiatives receive initial funding tranches to support discovery and experimentation.

- Teams use this to validate feasibility, desirability, and viability.

- Only after validation do teams make High Integrity Commitments, unlocking further funding.

Inspired by The Startup Way’s metered funding and EDGE’s incremental investment.

### 3. Outcome-Based Investment via OKRs

- Funding is tied to Objectives and Key Results (OKRs), not feature lists.

- OKRs define the measurable change the investment is expected to produce.

- Progress is reviewed quarterly, using telemetry and flow metrics—not status reports.

Aligns with Sooner Safer Happier’s BVSSH (Better Value Sooner Safer Happier) model.

### 4. Flow-Based Governance via Portfolio Kanban

- Portfolio Kanban visualizes initiative flow, dependencies, and WIP limits.

- Leaders use flow and outcome signals to coach teams and reallocate funding dynamically.

- Initiatives that stall or fail to validate assumptions can be paused, pivoted, or retired.

This replaces deterministic budgeting with empirical, adaptive governance.

### 5. Quarterly Cadence for Funding Decisions

- Funding decisions are made during Slowification windows (Weeks 1–2 and Week 12).

- Teams present validated hypotheses, outcome telemetry, and improvement OKRs.

- Leadership reviews evidence, not estimates, to guide investment.

### 6. Innovation Accounting Integration

- EmergentOS supports three levels of innovation accounting:

  - Learning Metrics: e.g. experiment velocity, discovery outcomes.

  - Behavioural Metrics: e.g. user engagement, conversion rates.

  - Business Metrics: e.g. revenue impact, cost reduction.

- These are tracked via telemetry dashboards, OKRs, and Flow Metrics.

The EmergentOS funding model transforms investment from a static, upfront allocation into a dynamic, evidence-based process that evolves with learning. By tying funding to validated hypotheses, measurable outcomes, and flow-based governance, it enables organizations to invest in what works—while safely stopping what doesn’t. This approach empowers teams, accelerates innovation, and ensures that every pound spent is traceable to strategic impact. In doing so, EmergentOS turns funding into a strategic lever for adaptability, not a constraint on it.

## Budgeting Guidance for Adaptive Funding in EmergentOS

This section provides practical guidance for finance and portfolio teams transitioning from traditional budgeting approaches to the adaptive, outcome-driven funding model used in EmergentOS. It outlines how to align financial planning with strategic agility, validated learning, and continuous value delivery.

### 1. Budgeting by Strategic Theme and Lean Value Tree Branches

- Allocate budgets to strategic themes and Lean Value Tree branches, not fixed projects.

- Treat each branch as a portfolio of bets—each with its own hypothesis and outcome targets.

- Enable modular funding that can be scaled up or down based on validated progress.

### 2. Use Metered Funding Tranches

- Replace large upfront allocations with metered funding tranches released quarterly.

- Initial tranches support discovery and experimentation.

- Subsequent tranches are contingent on validated learning, telemetry, and High Integrity Commitments.

This reduces financial risk and increases responsiveness to change.

### 3. Tie Funding to OKRs and Outcomes

- Require teams to define Objectives and Key Results (OKRs) before receiving funding.

- Key Results should reflect customer impact, business performance, or flow improvement.

- Use OKR progress as a signal for continued investment—not just delivery status.

### 4. Enable Dynamic Reallocation

- Use Portfolio Kanban and Flow Metrics to monitor initiative health and progress.

- Reallocate funding dynamically based on:

  - Hypothesis validation

  - Outcome achievement

  - Flow efficiency

  - Strategic shifts

This supports continuous prioritization and avoids sunk cost traps.

### 5. Support Innovation Accounting

- Track funding against three levels of innovation accounting:

  - Learning Metrics (e.g. experiment velocity)

  - Behavioural Metrics (e.g. user engagement)

  - Business Metrics (e.g. revenue impact)

- Use these metrics to assess return on learning before traditional ROI is visible.

### 6. Align Budgeting Cadence with EmergentOS Quarterly Cycle

- Sync budgeting reviews with Slowification windows (Weeks 1–2 and Week 12).

- Use these windows to:

  - Review validated learning

  - Assess OKR progress

  - Adjust funding allocations

  - Plan next quarter’s investments

### 7. Empower Teams with Guardrails

- Empower teams to make local investment decisions within defined guardrails:

  - Budget caps per initiative

  - Outcome-based funding gates

  - Shared telemetry dashboards

This decentralizes decision-making while maintaining financial discipline.

EmergentOS budgeting shifts the focus from predictive control to adaptive enablement. Finance and portfolio teams become strategic partners in learning, innovation, and value delivery—ensuring that every investment is traceable to outcomes, not just activity.

# Pattern: Outcome Over Output

## Context

Your organization is operating within a delivery model that emphasizes predictability, feature completion, and detailed planning. While this approach has provided structure, it may limit innovation, team engagement, and clarity around customer impact. Leadership expresses a desire for greater agility and responsiveness, but current practices tend to favour control and certainty over adaptability and learning.

## Problem

Traditional delivery frameworks (such as SAFe® or waterfall) often prioritize structure and predictability, which can provide a sense of control. However, this emphasis can unintentionally limit adaptability and responsiveness to change. Teams may be evaluated primarily on output volume rather than impact, and planning tends to be linear and deterministic, leaving limited space for iterative learning and course correction.

## Forces

- Stakeholders want visibility and certainty.

- Teams crave autonomy and purpose.

- Customers need solutions, not features.

- Estimation is unreliable but still expected.

- Change feels risky, but stagnation is worse.

## Solution

Introduce EmergentOS as a modular, evidence-based operating system. Start with a few teams. Use OKRs to shift focus from output to outcomes. Visualize work with Kanban. Embed Lean Kata and Flow Engineering to foster continuous improvement. Replace estimation with experimentation. Empower teams to make high-integrity commitments based on validated discovery.

## Result

Teams begin to own outcomes, not just tasks. Delivery becomes adaptive, not predictive. Flow improves. Customer impact becomes visible. Leadership shifts from control to coaching. The organization learns faster and delivers smarter.

## Related Patterns

- Evangelist: Identify a champion to introduce the operating system.

- Time for Reflection: Use quarterly cadence and retrospectives.

- Big Picture: Use outcome mapping to align strategy.

# Pattern: Legacy to Learning

## Context

Your organization is replacing a legacy system with a new platform. The work appears predictable—re-implementing known features—but hidden complexity, integration challenges, and outdated assumptions threaten delivery confidence.

## Problem

Teams assume the work is deterministic and plan using fixed milestones. But legacy systems are poorly documented; dependencies are unclear, and parity does not guarantee value. Delivery slips, and learning is lost.

## Forces

- Stakeholders expect certainty and parity.

- Teams face hidden complexity and integration risks.

- Legacy behaviour is often undocumented or misunderstood.

- Pressure to deliver quickly undermines discovery and validation.

## Solution

Run EmergentOS to shift from deterministic reimplementation to outcome-driven migration. Use OKRs to define strategic outcomes (e.g. reduced support tickets, improved performance). Run validated discovery to confirm feasibility before committing. Use Kanban to visualize migration flow and Lean Kata to improve delivery. Empower teams to make high-integrity commitments based on evidence.

## Result

Migration becomes iterative, resilient, and outcome focused. Teams uncover hidden risks early, validate assumptions, and deliver with confidence. Legacy is replaced not just with parity—but with learning, improvement, and measurable impact.

## Related Patterns

- Outcome Over Output

- High Integrity Commitments

- Time for Reflection

- Big Picture

# EmergentOS Values

1. Outcome Over Output

We prioritize measurable impact over activity. Success is defined by the change we create—not the volume we deliver.

2. Empowered Autonomy

Teams are trusted to own their outcomes, make decisions, and learn through experimentation. Leadership enables, not controls.

3. Evidence-Driven Learning

We make decisions based on data, telemetry, and validated discovery—not assumptions or estimates. Learning is continuous and embedded.

4. Flow and Focus

We optimize flow, reduce friction, and visualize work to stay focused on what matters. Bottlenecks are surfaced and addressed collaboratively.

5. Sustainable Pace

We deliver at a resilient rhythm that supports long-term performance, wellbeing, and innovation. Slowification is a strategic investment.

6. Strategic Alignment

Every initiative is connected to a clear strategic outcome. Lean Value Trees visualize the hierarchy of strategic themes, bets, and initiatives, while OKRs guide priorities and measure impact. Together, they ensure work is traceable to business value, adaptable as new insights emerge, and focused on solving the right problems—not just delivering outputs.

7. Coaching Culture

Leaders act as coaches, fostering growth, clarity, and capability. Governance is developmental, not directive.

8. Modular Adaptability

We evolve continuously. Practices are composable, scalable, and tailored to team maturity and context.

9. Customer-Centricity

We solve real problems for real people. Customer outcomes are the north star of our planning, delivery, and improvement.

10. Transparency and Trust

Work is visible, progress is shared, and decisions are made openly. Trust is built through clarity and accountability.

11. Hypothesis-Driven Strategy

We treat strategy as a series of bets, not certainties. Every initiative starts with a clear hypothesis and expected outcome, validated through discovery and learning before commitment. This ensures adaptability and reduces waste.

# Alignment with Simplyhealth’s Values

Courage and Curiosity

- Ambition and boundary-pushing: EmergentOS (EOS) encourages stretch OKRs, experimentation, and continuous discovery, which directly support bold goals and innovation.

- Speaking up and challenging norms: Practices like Lean Kata, Flow Engineering, and team retrospectives create safe spaces for teams to challenge assumptions and improve how they work.

- Curiosity and learning: EOS embeds empirical learning, experimentation, and validated discovery as core routines, fostering a culture of curiosity and growth.

Fit: Strong alignment with an emphasis on experimentation, learning, and challenging the status quo.

Trust and Kindness

- Trust through autonomy: EmergentOS decentralizes control, empowering teams to make decisions and own outcomes—building trust through accountability.

- Kindness through coaching: Governance is reframed as developmental, with leaders acting as coaches rather than controllers.

- Diversity and inclusion: The use of Team Topologies supports designing teams around cognitive load and interaction modes, which can help create inclusive, psychologically safe environments.

Fit: EmergentOS supports trust-building through autonomy and kindness through coaching and inclusive team design.

All Together Healthier

- Customer-centric healthcare solutions: EmergentOS is built around customer outcomes, not feature delivery—ensuring that work is meaningful and impactful.

- Collaboration and innovation: Cross-functional, stream-aligned teams and shared rituals (e.g. OKR planning, retrospectives) foster collaboration and innovation.

- Wellbeing and sustainable pace: The concept of Slowification is embedded to promote resilience, reduce burnout, and support self-care—aligning directly with your focus on colleague wellbeing.

Fit: EmergentOS’s emphasis on sustainable delivery, customer impact, and team health strongly supports this value.

# Core Principles

EmergentOS is built upon eight core principles (and one supporting principle):

### 1. Outcome-Driven Planning

- Delivery is aligned to customer outcomes, not feature roadmaps.

- Lean Value Trees (LVTs) provide the strategic map, breaking down themes into bets and initiatives.

- Teams use OKRs to focus on measurable impact and strategic alignment.

- Planning is quarterly, adaptive, and based on validated learning—not estimates.

### 2. Hypothesis-Driven Strategy

- Every initiative starts with a clear hypothesis and expected outcome.

- Hypotheses are validated through discovery and experimentation before commitment.

- This approach reduces waste and ensures adaptability.

### 3. Team-Centric Autonomy

- Teams are stream-aligned, cross-functional, and empowered to own outcomes.

- Decision-making is decentralized, supported by Team Topologies and clear interaction modes.

- Autonomy is balanced with strategic clarity through shared rituals and coaching.

### 4. Flow-Based Delivery

- Work is visualized and managed through Kanban, with WIP limits and flow metrics.

- Delivery is iterative, emphasizing thin slices, experimentation, and telemetry.

- Portfolio Kanban enables leaders to coach through flow—not control through timelines.

### 5. Continuous Improvement

- Teams run Lean Kata cycles and use Flow Engineering to identify and address systemic blockers.

- Improvement work is tracked as OKRs and reviewed quarterly alongside delivery goals.

- Learning is embedded into the rhythm of delivery—not treated as a separate activity.

### 6. Engineering Excellence

- Practices like CI/CD, trunk-based development, and infrastructure-as-code enable fast, safe delivery.

- DORA metrics provide empirical insight into engineering health and guide coaching.

- Technical quality is maintained through telemetry, automated testing, and safe deployment strategies.

### 7. Empirical Governance

- Governance is lightweight, developmental, and data-driven.

- Leaders guide teams using flow metrics, DORA trends, and validated outcomes—not timelines or estimates.

- Coaching-led governance includes OKR reviews, strategy refreshes, and coaching playbooks.

### 8. Sustainable Pace and Resilience

- The principle of Slowification ensures teams invest in planning, learning, and self-care.

- Delivery is paced to avoid burnout and support long-term performance.

- Teams are encouraged to pause, reflect, and improve continuously.

### 9. Methodology Flexibility

Within the quarterly cadence of EmergentOS, teams are fully empowered to choose and apply any delivery methodology—Agile or otherwise—that best suits their context.

The guiding principle is adaptability:

- If learning reveals that a chosen method impedes flow or limits outcomes, teams should evolve or replace it.

- EmergentOS provides scaffolding for this evolution through empirical governance, coaching-led support, and modular practices.

# Core Domains

Each domain within the operating system represents a dimension of adaptation – where change, learning, and alignment occur in a complex socio-technical system.

| Domain | Focus | Core Question | Primary Levers |
| --- | --- | --- | --- |
| Direction & Purpose | Strategy and shared outcomes | Why are we adapting? | Mission clarity, adaptive strategy, outcome definition, sensing mechanisms |
| Leadership & Culture | Behaviours, values, and psychological conditions | How do we lead and learn together? | Leadership models, decision rights, trust, learning culture, psychological safety |
| Product & Value Creation | Discovery, delivery, and validation of value | How do we create and evolve value continuously? | Product operating model, empowered teams, discovery practices, outcome metrics |
| Flow & Enablement | Technical and organizational infrastructure for adaptability | How do we make adaptation possible and safe? | Continuous Integration, Continuous Delivery, DevOps, automation, architecture, toolchains, system design for flow |
| Learning & Sensing | Feedback loops and systemic learning | How do we know what is working and what is not? | Retrospectives, reflection, experimentation, data feedback, sensing networks |

## Domain Relationships

These domains are interdependent and cyclic rather than hierarchical:

Each domain feeds the next:

- Purpose defines intent

- Leadership shapes the environment for teams

- Product teams create adaptive value

- Flow enables responsiveness

- Learning feeds insight back into strategy and culture

Across these domains, EmergentOS emphasises a few universal principles:

- Empowerment over control

- Outcomes over outputs

- Learning over certainty

- Trust over compliance

- Flow over friction

- Systems thinking over silos

# Why Flow Matters—and How EmergentOS Makes It Happen

Ever since Toyota introduced its Production System in the mid-20th century, manufacturers have understood the importance of flow in the production of value. Modern car manufacturers thoughtfully and intentionally optimize their operations around the production line, with the express intent of continually improving flow along the entire value stream. Modern production lines are deliberately designed to be adaptable and are constantly reconfigured and evolved to meet the needs of newer models and to maintain optimal flow.

Unlike these manufacturers—and some highly successful tech businesses that invest as much effort into creating flow as they do into creating products—many technology-driven product companies focus almost exclusively on what they deliver, paying little attention to how they deliver it. When optimization occurs, it often targets output volume rather than the flow of value. This leads to inefficiencies, bottlenecks, a buildup of technical debt, and reactive delivery practices that undermine adaptability and customer impact. In contrast with the forward-thinking car manufacturers, these companies typically apply the same delivery practices and techniques that they have always used for every product. They rely on rigid, deterministic planning models and centralized governance, assuming that what worked before will work again—despite increasing complexity and uncertainty. This lack of adaptability creates friction across the value stream, slows time-to-value, and disconnects teams from customer outcomes. Without deliberate investment in flow, organizations struggle to respond to change, scale effectively, and deliver meaningful business impact.

EmergentOS changes this paradigm. It enables organizations to optimize for value stream flow by embedding practices that make flow visible, measurable, and continuously improvable:

- Portfolio and Team Kanban: Visualize work across discovery, delivery, and improvement tracks.

- Flow Engineering: Map current and future states of value streams, identify systemic blockers, and design experiments for improvement.

- Lean Improvement Kata: Institutionalize small, iterative changes that enhance flow predictability and reduce waste.

- Team Topologies: Structure teams to minimize handoffs and cognitive load, accelerating throughput.

- CI/CD and DORA Metrics: Ensure technical practices support fast, safe delivery and provide empirical insight into flow health.

- Slowification Windows: Create deliberate space for reflection and improvement, preventing burnout and enabling sustainable flow.

By operationalizing these principles, EmergentOS transforms flow from an abstract concept into a strategic lever for adaptability and performance—helping organizations deliver outcomes faster, safer, and with greater confidence.

# Value Stream Management in EmergentOS

Value Stream Management (VSM) extends beyond mapping workflows—it is the discipline of measuring, visualizing, and optimizing the flow of value across the entire product delivery lifecycle. In the digital economy, organizations that manage value streams effectively outperform those that focus solely on output or isolated team metrics. VSM provides the bridge between business strategy and technology execution, ensuring that every investment drives measurable outcomes.

## How EmergentOS Operationalizes VSM

EmergentOS embeds Value Stream Management (VSM) principles into its operating rhythm through modular practices that make strategy-to-execution visible, measurable, and continuously improvable:

Lean Value Trees for Strategic Clarity

Visualize the hierarchy of strategic themes, bets, value streams, and initiatives, ensuring every investment is tied to measurable business outcomes. LVTs provide the strategic map that feeds into Portfolio Kanban.

Portfolio Kanban for Flow-Based Governance

Visualizes initiatives, dependencies, and alignment with OKRs across all streams. Leaders coach through flow and capacity signals—not timelines or estimates. WIP limits prevent overload and enable systemic improvement.

Flow Metrics + DORA Metrics for Empirical Governance

Combines Mik Kersten’s Flow Framework metrics (Velocity, Time, Efficiency, Load, Distribution) with DORA indicators (Deployment Frequency, Lead Time, Change Failure Rate, MTTR) to provide a holistic view of delivery health and adaptability.

Strategic Outcome Mapping + OKRs for Alignment

Links business objectives to measurable outcomes and team-level goals, ensuring prioritization reflects customer impact and validated hypotheses. OKRs cascade from LVT branches for consistency.

Flow Roadmaps for Continuous Improvement

Translates insights from Flow Engineering workshops into actionable improvement OKRs, embedding systemic learning into quarterly cycles. Improvement work is visible and prioritized alongside delivery.

## Why This Integration Strengthens EmergentOS

By explicitly incorporating VSM, EmergentOS moves beyond process optimization to strategic value delivery. It enables organizations to:

- Align technology investments with business outcomes.

- Optimize end-to-end flow across discovery, delivery, and improvement.

- Replace anecdotal reporting with empirical, outcome-driven governance.

- Scale adaptability without sacrificing clarity or autonomy.

In short: VSM transforms EmergentOS from an adaptive delivery system into a strategic operating model for competing in the digital economy.

# Alignment with the Three Ways of DevOps

EmergentOS aligns closely with the foundational principles of DevOps, known as the Three Ways:

## 1. The First Way: Flow (Systems Thinking)

EOS optimizes the flow of work from strategy to delivery through:

- Lean Value Trees for visualizing strategic bets and connecting them to delivery initiatives.

- Portfolio Kanban for managing flow across value streams and enabling systemic visibility.

- Team Topologies to reduce handoffs and cognitive load.

- CI/CD pipelines and trunk-based development for fast, safe, and continuous delivery.

- Flow Engineering and VSM to identify and remove systemic bottlenecks.

## 2. The Second Way: Feedback (Amplify Feedback Loops)

EOS embeds feedback loops at every level:

- Telemetry, Flow Metrics, and DORA indicators provide real-time insights into delivery health.

- Outcome Mapping, OKRs, and LVT hypotheses ensure customer feedback informs prioritization.

- Retrospectives and experimentation validate assumptions and guide improvement.

## 3. The Third Way: Continual Learning and Experimentation

EOS fosters a culture of learning through:

- Lean Improvement Kata and Flow Roadmaps for structured, iterative improvement.

- Slowification windows to create space for reflection, learning, and capability building.

- Coaching-led governance and High Integrity Commitments to support safe experimentation and evidence-based planning.

This alignment ensures that EOS not only supports agile delivery but also reinforces the cultural and operational foundations of high-performing DevOps organizations.

# Alignment with Lean Thinking

EmergentOS operationalizes Lean Thinking principles at scale, ensuring that value delivery is efficient, customer-focused, and continuously improving. Below is how EmergentOS aligns with the five core principles of Lean:

1. Value

- Uses Lean Value Trees (LVTs) and Strategic Outcome Mapping to define value in terms of measurable outcomes—not outputs.

- OKRs cascade from LVT branches, ensuring alignment with strategic bets.

- Validated Discovery and hypothesis-driven planning ensure teams build what customers need, reducing waste.

2. Value Stream

- Applies Value Stream Management (VSM), Flow Engineering, and Portfolio Kanban to visualize and optimize end-to-end flow.

- Teams are organized using Team Topologies, reducing dependencies, and improving throughput across streams.

3. Flow

- Enforces Work-In-Progress (WIP) limits, Kanban systems, and CI/CD pipelines to maintain continuous delivery.

- Portfolio Kanban provides systemic visibility and enables leaders to coach through flow—not control through timelines.

- Slowification windows create deliberate space for improvement without sacrificing flow.

4. Pull

- Promotes pull-based planning through Kanban and outcome-driven prioritization.

- Teams commit only after validated discovery and hypothesis testing, aligning with Lean’s pull principle.

5. Perfection

- Embeds Lean Improvement Kata and Flow Roadmaps for structured, iterative improvement.

- Telemetry, Flow Metrics, and DORA indicators provide empirical feedback to guide improvement toward perfection.

In essence, EmergentOS acts as a Lean Operating System for modern product delivery, combining Lean principles with DevOps, Agile, and systems thinking to create a scalable, outcome-driven approach to continuous improvement.

# Output Vs Outcomes

“Success is not delivering a feature; success is learning how to solve the customer’s problem.”

— Eric Ries, The Lean Startup

Output

- Definition: The tangible deliverables a team produces—features, code, designs, documents.

- Example: “We shipped a new onboarding flow” or “We released version 2.0 of the app.”

- Focus: Activity and delivery volume.

Outcome

- Definition: The measurable change or impact resulting from what was delivered—on customer behaviour, business performance, or system health.

- Example: “Onboarding completion rate increased from 60% to 90%” or “Customer retention improved by 15%.”

- Focus: Value and effectiveness.

In many organizations, success is measured by how much gets shipped—how many features, releases, or deliverables are completed. This is output: the tangible work produced by a team. It is easy to count, easy to report, and often mistaken for progress. But output alone does not tell you whether the work made a difference.

Outcomes, on the other hand, are the real-world changes that result from what was delivered. They reflect whether a feature improved customer behaviour, solved a problem, or moved a business metric. Outcomes are harder to measure, but they are what truly matters. A new onboarding flow is output; a 30% increase in onboarding completion is an outcome.

Strong product teams understand this distinction. They do not just build—they learn. They define success in terms of customer impact, not code volume. They validate assumptions, run experiments, and iterate based on evidence. They use tools like OKRs to align their work with strategic goals, and telemetry to measure whether their solutions are working.

By focusing on outcomes, these teams avoid the trap of building for the sake of building. They prioritize what matters, adapt quickly, and deliver value—not just velocity. In doing so, they earn trust, drive innovation, and make a meaningful difference.

## Five Signs of an Output Focused Organization

The following is a not-exhaustive list of behaviours that indicate the organization is focused more on outputs rather than outcomes.

1. Roadmaps are fixed and feature-led

- Roadmaps are long lists of features with dates, handed down from leadership.

- There’s little room for experimentation, reprioritization, or learning.

2. Discovery is siloed or skipped

- Product discovery is done by product managers or designers alone.

- Engineers are brought in only after decisions are made.

- Customer interviews and usability testing are rare or absent.

3. Requirements are handed down, not co-created

- Teams wait for “the business” or “stakeholders” to define what to build.

- There is little questioning whether the requirement solves a real problem.

4. No telemetry or outcome validation

- Features are shipped without instrumentation.

- Teams do not track usage, behaviour change, or business impact post-release.

5. OKRs (if used) are output-based

- Objectives are framed as “Launch X” or “Build Y” rather than “Improve Z metric” or “Solve customer problem A.”

- Key results measure completion, not change.

# EmergentOS Components

## Jonathan Smart’s Ways of Working Centre of Enablement

The guide: The Centre of Enablement embeds adaptive learning into EmergentOS, equipping teams to adopt proven practices that improve outcomes.

- In action: The WoW CoE provides coaching and guidance, leveraging patterns and playbooks to help teams become self-sufficient and empowered.

- Why it matters: It decentralizes expertise, accelerates learning, and amplifies autonomy—fostering adaptability and continuous improvement across the value stream.

## Marty Cagan’s Product Operating Model

The foundation: This model anchors the EmergentOS in customer outcomes and team empowerment. Product teams are cross-functional, autonomous, and accountable for delivering real value—not just shipping features.

- In action: Each team owns a slice of the customer experience. They define problems worth solving, validate solutions through discovery, and deliver iteratively.

- Why it matters: It decentralizes decision-making and puts product, design, and engineering in the driver’s seat.

## Lean Value Trees & OKRs for Strategic Alignment

The compass: OKRs translate strategy into quarterly, team-level goals. They focus effort on the most important outcomes and create alignment without micromanagement.

- In action: Strategic themes and bets are first mapped in Lean Value Trees, which break down high-level objectives into value streams and initiatives.

Teams then set OKRs that cascade from these LVT branches, ensuring every key result ties back to a strategic hypothesis.

These OKRs guide prioritization and are reviewed weekly alongside Kanban boards, which visualize delivery flow.

- Why it matters: It replaces estimation-driven planning with outcome-driven focus, while LVTs ensure that OKRs are not created in isolation but grounded in strategic bets and value hypotheses.

Together, LVTs and OKRs create a closed loop: strategy → prioritization → execution → feedback → strategy refresh.

## Team Topologies for Scalable Structure

The architecture: Team Topologies defines how teams are structured and interact—stream-aligned, enabling, platform, or complicated subsystem—with clear interaction modes.

- In action: Dependencies are managed through service relationships, not planning ceremonies. Enabling teams coach others on CI/CD, platform teams abstract complexity.

- Why it matters: It reduces coordination overhead and cognitive load, enabling faster flow.

## Kanban for Flow Visualization

The dashboard: Kanban boards make work visible, track flow, and highlight blockers. They are used at both team and portfolio levels.

- In action: Teams visualize discovery, delivery, and improvement work. WIP limits and flow metrics guide daily standups and retros.

- Why it matters: It replaces Gantt charts and PI plans with real-time delivery insight.

## Lean Improvement Kata + Flow Engineering

The engine: These techniques drive continuous improvement of delivery processes. Kata provides a structured routine for experimentation; Flow Engineering and its Value Stream Mapping techniques reveal systemic bottlenecks.

- In action: Teams run quarterly Kata cycles to improve flow, reduce handoffs, or shorten lead time. Flow Engineering workshops identify where work stalls across the value stream.

- Why it matters: It embeds a culture of learning and operational excellence.

## Engineering Best Practices + CI/CD

The delivery pipeline: Engineering teams adopt trunk-based development, automated testing, and infrastructure-as-code to enable rapid, reliable delivery.

- In action: Features are deployed via CI/CD pipelines with telemetry and rollback. Feature toggles allow safe experimentation.

- Why it matters: It enables speed without sacrificing stability.

## DORA and Flow Metrics for Performance Insight

The scorecard: Deployment Frequency, Lead Time for Changes, Change Failure Rate, and Mean Time to Recovery are tracked to measure engineering health. Flow Metrics complement these by adding Flow Velocity, Flow Efficiency, Flow Time, Flow Load, and Flow Distribution to assess value stream health.

- In action: Teams review DORA and Flow metrics monthly to correlate delivery practices with outcomes and identify systemic bottlenecks. Leaders use trends—not targets—to guide coaching and improvement experiments. Flow metrics highlight where work stalls while DORA metrics validate engineering stability.

- Why it matters: Combining DORA and Flow metrics replaces anecdotal performance reviews with empirical data, providing a holistic view of speed, stability, and adaptability. This enables evidence-based governance and continuous improvement across both technical and business dimensions.

# EmergentOS Component Relationship Model

# Slowification

Slowification, as introduced by Gene Kim and Steve Spear in Wiring the Winning Organization, refers to the deliberate act of slowing down to speed up—investing time in planning, practice, and learning to build resilience, reduce risk, and improve long-term performance. It is about creating space for teams to hone their craft, develop routines, and solve problems thoughtfully, especially in high-stakes environments where reactive work leads to burnout and technical debt.

Slowification is the concept that underpins EmergentOS with its emphasis on empirical learning, continuous improvement, and team empowerment. Here is how it is embedded:

Quarterly Cadence

- Week 1–2: The Slowification window—dedicated time for teams to reflect, learn, and prepare before diving into delivery.

- Week 12: Retrospectives are not just for reviewing outcomes, but for identifying where teams need to slow down to improve—whether through training, refactoring, or process redesign.

## Lean Kata & Flow Engineering

- Slowification aligns with the Improvement Kata: teams deliberately pause to assess current conditions, define target states, and run experiments.

- It complements Flow Engineering by encouraging teams to address systemic blockers before rushing into execution.

## Governance & Coaching

- Leaders can use coaching rituals to promote Slowification: asking teams where they need time to sharpen skills, reduce complexity, or rethink assumptions.

- Governance shifts from enforcing speed to enabling sustainable flow.

## Engineering Practices

- Encourage technical Slowification: time for refactoring, improving CI/CD pipelines, and reducing tech debt.

- Use DORA metrics to identify when rushing is degrading performance—and where slowing down could improve stability and recovery.

By embracing Slowification, organizations foster resilience, reduce burnout, and create space for meaningful improvement—ensuring that speed is sustainable, and outcomes are reliable.

## Pattern: Time for Reflection

### Context

Teams are under constant pressure to deliver. Work moves from one cycle to the next without pause. Retrospectives are rushed or skipped, and improvement work is deprioritized. Burnout rises, and learning stagnates.

### Problem

Without dedicated time for reflection, teams fail to identify systemic issues or learn from experience. Delivery becomes reactive, technical debt accumulates, and adaptability suffers.

### Forces

- Stakeholders push for continuous output and speed.

- Teams feel guilty taking time away from delivery.

- Improvement work is invisible and undervalued.

- Short-term deadlines overshadow long-term resilience.

### Solution

Deliberately schedule Slowification windows for reflection and learning. With EmergentOS, this happens during Week 1–2 (before execution) and Week 12 (after delivery). Use these windows for:

- Reviewing OKRs and outcomes.

- Running retrospectives focused on both delivery and learning.

- Identifying systemic blockers through Flow Engineering.

- Planning improvement experiments using Lean Kata.

Normalize reflection as a strategic investment, not a luxury. Leaders should coach teams to prioritize improvement work alongside delivery.

### Result

Teams gain clarity, reduce burnout, and improve continuously. Delivery becomes more predictable and resilient. Learning drives innovation and adaptability, making the organization stronger over time.

### Related Patterns

- Outcome Over Output

- Legacy to Learning

- Flow First

- Coaching Culture

# Team Topologies

“Team Topologies provides a much-needed framework for evaluating and optimizing team organization for increased flow.”

— Matthew Skelton & Manuel Pais, Team Topologies25

## Principles & Purpose

Team Topologies26, developed by Matthew Skelton and Manuel Pais, is a modern approach to structuring software teams for fast flow, clear ownership, and scalable collaboration. It emphasizes designing team interactions intentionally to reduce cognitive load and improve delivery speed.

### Core Principles:

- Optimize for Flow of Change: Structure teams to reduce handoffs and delays.

- Limit Cognitive Load: Teams should only own what they can understand and manage effectively.

- Encourage Team Evolution: Team structures should adapt as systems and needs evolve.

- Use Well-Defined Interaction Modes: Collaboration should be purposeful and predictable.

## Why It is a Good Fit for EmergentOS

This outcome-driven operating system prioritizes autonomy, empirical learning, and modular delivery—all of which are reinforced by Team Topologies:

- Decentralized Dependency Management: Instead of managing dependencies through planning ceremonies, teams interact via service relationships.

- Stream-Aligned Ownership: Teams own slices of the customer journey, enabling faster decision-making and clearer accountability.

- Scalable Coaching & Enablement: Enabling teams support others without becoming bottlenecks.

- Reduced Coordination Overhead: Clear interaction modes prevent misalignment and rework.

## Team Types

| Team Type | Purpose | Example Role |
| --- | --- | --- |
| Stream-Aligned Team | End-to-end delivery of customer value | Product feature team |
| Enabling Team | Help other teams adopt new practices or tech | DevOps coaching team |
| Platform Team | Provide reusable services and infrastructure | Internal API or cloud tooling team |
| Complicated Subsystem Team | Own deep technical areas requiring specialist knowledge | ML model team or algorithmic engine team |

### Interaction Modes

| Mode | Purpose | When to Use |
| --- | --- | --- |
| Collaboration | Work together on a shared goal | Short-term joint initiatives |
| X-as-a-Service | One team provides a service to another | Platform or reusable capability |
| Facilitating | One team helps another learn or adopt something | Coaching, onboarding, or tech enablement |

## Cross-Functional Teams

### Definition

A cross-functional team in EmergentOS is a stream-aligned team that includes all roles necessary to discover, deliver, and validate customer outcomes autonomously—without relying on handoffs for core work.

Core Roles:

- Value Outcome Lead (VOL) – Owns outcomes and prioritization.

- Architecture Outcome Lead (AOL) – Safeguards technical integrity.

- Product Designers & Engineers – Collaborate on discovery and delivery.

Broader functions (e.g., finance, legal, compliance) interact through defined interaction modes—such as facilitating or X-as-a-service—rather than embedding in every squad.

### Principles

- End-to-End Ownership
Teams own a slice of the customer journey, from problem discovery to outcome validation.

- Minimal Handoffs
Core skills for discovery and delivery are inside the team; external dependencies are managed through service relationships.

- Autonomy with Alignment
Teams operate independently but align through OKRs, Lean Value Trees, and Portfolio Kanban.

- Interaction Modes, Not Silos
Use Team Topologies’ modes—Collaboration, Facilitating, X-as-a-Service—to engage enabling and platform teams.

### Common Misconceptions

- Myth: Cross-functional means “everyone in one team” (legal, finance, ops).

Reality: Include only roles essential for discovery and delivery; others support via interaction modes.

- Myth: Cross-functional equals “project team.”
Reality: EmergentOS teams are long-lived, outcome-focused, not temporary project groups.

### How It Scales

- Team Level: Stream-aligned teams are cross-functional by default.

- Value Stream Level: Multiple stream-aligned teams collaborate with enabling and platform teams for systemic capabilities.

## Strategic Impact

- Faster Flow: Teams are structured to minimize delays and handoffs.

- Clearer Ownership: Each team knows its scope and responsibilities.

- Better Dependency Management: Interactions are designed, not improvised.

- Scalable Autonomy: Teams can evolve independently while staying aligned.

## Pattern: Team Topologies

### Context

Your organization struggles with delivery speed and coordination. Teams are organized around projects or technologies, leading to frequent handoffs, unclear ownership, and high cognitive load. Dependencies slow progress, and collaboration feels reactive rather than intentional.

### Problem

Traditional team structures create bottlenecks and silos. Work stalls because teams depend on others for critical capabilities. Coordination overhead grows as systems scale, reducing adaptability and increasing frustration.

### Forces

- Stakeholders want predictability and speed.

- Teams need clarity of ownership and reduced cognitive load.

- Dependencies are inevitable but unmanaged.

- Scaling amplifies complexity and communication challenges.

### Solution

Apply Team Topologies principles to design team structures for fast flow and clear ownership. Organize teams into four types—Stream-Aligned, Enabling, Platform, and Complicated Subsystem—and define interaction modes (Collaboration, X-as-a-Service, Facilitating). Use topology tune-ups to adapt structures as systems evolve. Empower stream-aligned teams to own end-to-end delivery of customer value, supported by enabling and platform teams that reduce friction.

### Result

Teams experience fewer handoffs and clearer boundaries. Cognitive load decreases, enabling faster decision-making and higher autonomy. Dependencies are managed through designed interactions, not ad hoc coordination. Delivery accelerates, and adaptability improves as team structures evolve with the system.

### Related Patterns

- Outcome Over Output

- Coaching Culture

- Flow First

# Ways of Working Centre of Enablement

“In order to be successful, there is a need for people who are dedicated full time in a servant leader capacity to orchestrate the improvement of the system of work across an organization”

— Jonathan Smart, Sooner Safer Happier

In his book Sooner Safer Happier, Jonathan Smart describes the concept of a Ways of Working Centre of Enablement (WoW CoE). It is presented as a pattern for scaling better ways of working without creating bottlenecks or command-and-control structures.

## Purpose

The Ways of Working Centre of Enablement in EmergentOS exists to accelerate the adoption of modern practices and improve outcomes across value streams. Its mission is to enable autonomy, amplify learning, and scale successful patterns.

## Core Principles

- Enablement, Not Ownership

  - The WoW CoE does not own delivery or enforce compliance.

  - It provides coaching, guidance, and reusable assets to help teams succeed independently.

- Decentralized Empowerment

  - Equip teams with knowledge, tools, and patterns, not mandates.

  - Act as a servant leader, enabling teams to adopt practices that improve outcomes.

- Community and Learning

  - Foster communities of practice for experimentation and shared learning.

  - Scale successful patterns through social proof, not top-down directives.

- Outcome-Oriented

  - Measure success by business outcomes, not compliance with frameworks.

  - Continuously ask: Are we helping teams deliver better value sooner, safer, and happier?

## Interaction with Delivery Managers

- Flow Enablement
Provide frameworks, metrics, and coaching to help DMs identify systemic impediments and improve flow.

- Practice Adoption
Support DMs in embedding Agile, Lean, and DevOps practices without imposing rigid processes.

- Continuous Improvement
Collaborate with DMs to run improvement experiments and share learnings across teams.

## Interaction with Product Teams

- On-Demand Expertise
Offer guidance on Agile practices, metrics, and scaling patterns when teams need help.

- Autonomy Enablement
Help teams become self-sufficient by providing templates, playbooks, and coaching.

- Community Building
Connect teams through communities of practice to share insights and accelerate learning.

## Benefits

- Faster adoption of modern ways of working.

- Reduced duplication of effort across teams.

- Improved consistency without slowing delivery.

- Stronger alignment between strategy, delivery, and technical excellence.

# The Product Operating Model: What It Is

“The product operating model is about consistently creating technology-powered solutions that your customers love, yet work for your business.”

— Marty Cagan, Empowered

The Product Operating Model—popularized by thought leaders like Marty Cagan—is a modern approach to organizing product teams around customer outcomes, empowered autonomy, and continuous discovery and delivery. It replaces traditional project-based, and other waterfall-like models with cross-functional, stream-aligned teams that own end-to-end slices of the customer journey.

## Why It is So Successful

Customer-Centric

- Teams focus on solving real problems for users, not just delivering features.

- Success is measured by validated impact, not output volume.

Empowered Teams

- Product, design, and engineering collaborate closely.

- Teams are trusted to make decisions and experiment rapidly.

Continuous Discovery & Delivery

- Discovery is not a phase—it is ongoing.

- Teams validate ideas early through prototypes, A/B tests, and telemetry.

Decentralized Decision-Making

- Strategy is aligned through OKRs, but execution is owned by teams.

- This reduces bottlenecks and increases speed.

Scalable & Adaptable

- The model scales through Team Topologies, enabling clear team interactions and reducing coordination overhead.

## Strategic Impact

- Faster Learning: Teams iterate quickly and learn from real user feedback.

- Greater Ownership: Teams feel responsible for outcomes, not just tasks.

- Better Prioritization: Work is guided by customer value, not stakeholder requests or estimates.

- Alignment Without Micromanagement: OKRs and outcome mapping provide strategic clarity while preserving autonomy.

## The Value Outcome Lead (fka Product Manager)

Taking inspiration from BVSSH, EmergentOS adopts the name Value Outcome Lead (VOL), instead of Product Manager or Product Owner, to place strong emphasis on value and outcomes over product delivery.

In Marty Cagan’s Product Operating Model, and therefore EmergentOS, the Value Outcome Lead is a critical role within empowered, cross-functional teams. Unlike traditional project managers, VOLs do not manage schedules or task assignments—they own outcomes, not output.

### Core Responsibilities

- Define the Problem, Not the Solution
VOLs identify the most valuable customer and business problems to solve, using data, research, and strategic priorities.

- Own Value and Viability
They ensure that proposed solutions are desirable for customers, viable for the business, and aligned with organizational objectives.

- Collaborate Deeply
VOLs work closely with Product Designers and Engineers during both discovery and delivery, ensuring solutions are feasible, usable, and impactful.

- Prioritize for Impact
Using OKRs and evidence from discovery, VOLs prioritize work that delivers measurable outcomes rather than feature volume.

- Measure Success by Outcomes
VOLs track success through customer behaviour and business results, not just delivery milestones.

### What They Are Not

- Not a project manager or delivery manager—they do not own timelines or enforce plans.

- Not a boss—they are peers within the team.

- Not a feature order-taker—they focus on solving problems, not implementing requests.

## How Value Outcome Leads Use Discovery in EmergentOS

In EmergentOS, Value Outcome Leads play a critical role in ensuring that teams build the right solutions—not just deliver features. This is achieved through continuous product discovery, which runs in parallel with delivery and is embedded into the quarterly cadence.

### Purpose of Discovery

Discovery reduces uncertainty by validating that proposed solutions are:

- Valuable to customers

- Usable for end users

- Feasible for engineering

- Viable for the business

### Key Activities

- Define the Problem Space
VOLs work with stakeholders, data, and customer insights to identify the most impactful problems to solve.

- Collaborate on Solutions
VOLs partner with designers and engineers to explore multiple solution options, balancing desirability, feasibility, and viability.

- Validate Assumptions Early
Using experiments, prototypes, and user testing, VOLs ensure ideas are tested before significant investment.

- Prioritize Based on Evidence
Discovery outcomes inform backlog priorities and OKRs, ensuring work aligns with strategic goals and customer needs.

### Continuous, Not Sequential

Discovery is not a phase—it is an ongoing practice. VOLs continuously learn from customer feedback, product analytics, and market signals, adjusting priorities and shaping delivery in real time.

Result: Teams avoid the “feature factory” trap and focus on delivering measurable outcomes that matter to customers and the business.

The Four Big Risks in Product Discovery When evaluating ideas, product teams must address four critical risks before committing significant resources: - Valuable Will customers buy it or choose to use it? Ensures the solution solves a real problem and delivers meaningful value. - Usable Can users figure out how to use it easily? Focuses on intuitive design and user experience. - Feasible Can we build it with the time, technology, and skills we have? Validates technical viability early. - Viable Does this solution work for the business? Confirms alignment with business goals, legal constraints, and financial models. Why it matters: Addressing these risks during discovery prevents wasted effort and ensures teams build products that succeed in the market.

## Integrating Lean UX with EmergentOS

Lean UX is a design and product development approach focused on continuous learning, rapid experimentation, and outcome-driven work. EmergentOS incorporates Lean UX principles to ensure teams validate assumptions and deliver customer value iteratively.

### Why They Fit Together

Both Lean UX and EmergentOS share core beliefs:

- Outcomes over outputs.

- Cross-functional collaboration.

- Hypothesis-driven development.

- Continuous discovery and delivery.

EmergentOS provides the operating model that scales Lean UX practices across the enterprise.

### Integration Points

- OKRs as Outcome Anchors
EmergentOS uses OKRs (Who + Does What + By How Much) to define success in behavioural terms. Lean UX teams use these OKRs to frame hypotheses and experiments.

- Hypothesis-Driven Planning
 Initiatives in EmergentOS start as hypotheses:
 We believe [this outcome] will happen if [these outputs] are delivered.
 Lean UX provides the methods to test these assumptions quickly.

- Continuous Discovery Inside Stream-Aligned Teams
EmergentOS embeds discovery and delivery within the same team, aligning with Lean UX’s iterative approach.

- Portfolio-Level Support for Lean UX
 EmergentOS adds governance Lean UX doesn’t cover:

  - Portfolio Kanban for visualizing initiatives.

  - WIP limits to maintain flow.

  - Interaction modes for enabling teams (e.g., research specialists, compliance).

### Practical Workflow

- Step 1: Define OKRs
 Example: Existing customers increase repeat purchases by 15%.

- Step 2: Frame Hypotheses
 We believe improving checkout UX will increase repeat purchases by 15%.

- Step 3: Design Experiments
 Lean UX methods: prototypes, A/B tests, interviews.

- Step 4: Validate & Adapt
 If data shows no movement, pivot outputs or hypothesis.

#### Example

- Objective: Improve retention.

- Key Result: Reduce churn from 10% to 5%.

- Hypothesis: Adding personalized recommendations will reduce churn.

- Experiment: Launch prototype to 10% of users, measure churn impact.

## The Team Outcome Lead

Taking inspiration from BVSSH, EmergentOS adopts the name Team Outcome Lead (TOL), instead of Agile Coach, Scrum Master, or Delivery Manager, to place strong emphasis on the team and its ways of working.

The Team Outcome Lead in EmergentOS plays a critical role in ensuring that product teams deliver value efficiently and predictably within the value stream. While product managers focus on what to build and technical leads focus on how to build it, the TOL ensures that the flow of work across teams is smooth, dependencies are managed, and impediments are removed.

### Core Responsibilities

- Optimize Flow of Work
Ensure that prioritized items move through the delivery pipeline without unnecessary delays.

- Remove Blockers and Impediments
Actively identify and resolve issues that hinder progress, whether technical, organizational, or process-related.

- Manage Dependencies
Coordinate across teams and external stakeholders to reduce bottlenecks and sequencing issues.

- Capacity and Resource Planning
Work with technical leads and product managers to align team capacity with delivery commitments.

- Delivery Forecasting and Reporting
Provide visibility into progress, risks, and timelines without micromanaging teams.

### Key Principles

- Servant Leadership: Empower teams rather than control them.

- Flow over Deadlines: Focus on sustainable delivery and predictability, not arbitrary dates.

- Collaboration First: Work closely with Value Outcome Leads and Architecture Outcome Leads to balance priorities, technical feasibility, and delivery constraints.

### Position in the Value Stream

- Operates across multiple product teams (typically 2–3 teams per DM, depending on complexity).

- Interfaces with Portfolio and Program-level roles to ensure alignment with strategic objectives.

- Acts as a bridge between strategy and execution, ensuring that prioritized work translates into delivered outcomes.

### Role in Continuous Improvement

Within EmergentOS, the Team Outcome Lead is not just a facilitator of delivery; they are a continuous improvement leader. Their work is grounded in the Lean Improvement Kata mindset, ensuring that delivery practices evolve toward long-term flow optimization while addressing immediate impediments. The TOL is aided by the Ways of Working Centre of Enablement.

Lean Improvement Kata Orientation

- Long-Term Perspective
DMs maintain a vision of an ideal state where flow is predictable, dependencies are minimized, and teams operate autonomously.

- Iterative Improvement
Apply small, measurable steps toward improving delivery processes, guided by data and feedback loops.

- Scientific Thinking
Use hypothesis-driven experiments to validate changes before scaling them across the value stream.

Dual Focus on Impediments

- Acute Impediments
Quickly resolve blockers that threaten current delivery commitments (e.g., resource conflicts, technical bottlenecks).

- Systemic Impediments
Identify and address root causes that repeatedly disrupt flow (e.g., unclear role boundaries, dependency-heavy architecture).

Practices for Embedding Kata

- Regular Reflection Cycles
Incorporate retrospectives and flow reviews into the cadence of work.

- Visualize Flow Metrics
Uses the Flow Framework’s Flow Metrics and DORA metrics to identify improvement opportunities.

- Collaborate Across Roles
Work with PMs and TLs to ensure improvements align with product goals and technical feasibility.

Why This Matters
Operating within the Improvement Kata ensures that TOLs are not just reacting to problems but building a delivery system that gets better over time, reducing friction and increasing predictability across the value stream.

## The Architecture Outcome Lead

Taking inspiration from BVSSH, EmergentOS adopts the name Architecture Outcome Lead (AOL), instead of Technical Lead (Tech Lead).

In both Marty Cagan’s empowered product team model the Technical Lead/Architecture Outcome Lead is a critical role within the core team triad (Product Manager/Value Outcome Lead, Product Designer, Tech Lead). Their purpose is to ensure technical integrity while enabling speed and innovation.

### Core Responsibilities

- Set Technical Direction
Define and communicate architectural principles, ensure alignment with enterprise standards, and make key design decisions that support scalability and resilience.

- Champion Engineering Excellence
Promote best practices in coding, testing, and DevOps. Drive adoption of Continuous Integration (CI), Continuous Delivery (CD), and automation to improve flow efficiency.

- Mentor and Enable the Team
Support engineers through pairing, code reviews, and knowledge sharing. Foster a culture of learning and technical mastery.

- Remove Technical Blockers
Actively resolve impediments that slow delivery, ensuring teams can maintain momentum without compromising quality.

- Bridge Between Technology and Business
Translate technical trade-offs for non-technical stakeholders and ensure feasibility aligns with product goals and strategic outcomes.

### What They Are Not

- Not a task allocator or project manager.

- Not a bottleneck for decisions—they enable autonomy by setting clear technical guardrails.

### Why This Role Matters in EmergentOS

The Architecture Outcome Lead ensures that adaptability does not come at the cost of quality. By embedding technical leadership within the team, EmergentOS balances speed with sustainability, enabling teams to deliver continuously while evolving their architecture and practices.

## The Role of Product Engineers in EmergentOS

Marty Cagan emphasizes that empowered product teams require empowered engineers. When engineers are involved early and deeply, teams innovate faster, reduce waste, and build better products.

In EmergentOS, Product Engineers are more than implementers—they are full partners in discovery and delivery. Their role extends beyond writing code to actively shaping solutions that deliver measurable customer and business outcomes.

### Core Responsibilities

- Active in Discovery
Product Engineers collaborate with Product Managers and Designers during discovery to assess technical feasibility, explore solution options, and rapidly prototype ideas.

- Shared Accountability for Outcomes
Engineers share responsibility for achieving customer and business impact, not just shipping features. They contribute insights that influence prioritization and design decisions.

- Champion Technical Excellence
They advocate for modern engineering practices such as Continuous Integration (CI), Continuous Delivery (CD), automated testing, and observability—ensuring speed without sacrificing quality.

- Collaborative Problem-Solving
Engineers bring creativity to solution design, helping balance feasibility, value, and usability within the team’s strategic context.

### Why This Matters

By embedding engineers deeply in both discovery and delivery, EmergentOS avoids the “feature factory” trap. Teams innovate faster, reduce waste, and deliver solutions that are technically sound, customer-centric, and aligned with business goals.

Why Engineers Should Talk to Customers In empowered product teams, engineers are not just implementers—they are problem solvers. Direct interaction with customers gives engineers context and clarity, enabling better technical decisions and more innovative solutions. Benefits of Customer Interaction: - Deeper Understanding: Engineers hear real pain points, reducing reliance on second-hand interpretations. - Better Solutions: Early exposure to customer needs helps engineers propose creative, feasible approaches. - Shared Ownership: When engineers understand the “why,” they feel accountable for outcomes—not just output. How It Happens: - Join customer interviews and usability tests. - Observe real-world usage through shadowing or session recordings. - Participate in prototyping and validation sessions. Bottom Line: When engineers connect with customers, teams build products that are valuable, usable, feasible, and viable—the foundation of modern product discovery.

## Managing Role Boundaries in EmergentOS

In modern product organizations like EmergentOS, clarity of role boundaries is essential to prevent overlap and friction between Product Management, Delivery Management, and Technical Leadership. Here is how these boundaries can be defined and maintained:

### Core Responsibilities by Role

| Role | Primary Focus | Key Responsibilities |
| --- | --- | --- |
| Value Outcome Lead | Value & Outcomes | Define product vision, prioritize backlog, align with business goals, communicate “why” and “what.” |
| Team Outcome Lead | Flow & Execution | Ensure smooth delivery, manage dependencies, remove blockers, optimize team capacity, and track progress. |
| Architecture Outcome Lead | Technical Direction & Quality | Guides architecture and design decisions, maintain code quality, ensure technical feasibility, supports engineers in solving complex problems. |

### Where Overlap Happens

- Prioritization vs Scheduling
VOLs set priorities, but when they dictate timelines or resource allocation, they cross into TOL territory.

- Dependency Management
VOLs often identify dependencies for roadmap planning but resolving them operationally is TOL’s role.

- Technical Trade-offs
VOLs may influence scope for business reasons, but AOL owns decisions on feasibility and technical integrity.

### Principles for Healthy Boundaries

- Value Outcome Leads own the “Why” and “What,” not the “How.”

- Team Outcome Leads own the “How” and “When,” ensuring flow without compromising value.

- Architecture Outcome Leads safeguard technical integrity and feasibility.

- Shared visibility tools (roadmaps, Kanban boards, dependency maps) enable collaboration without micromanagement.

### Practical Guardrails

| Activity | VOL | TOL | AOL |
| --- | --- | --- | --- |
| Prioritization | Responsible | Consulted | Consulted |
| Delivery Scheduling | Consulted | Responsible | Informed |
| Technical Decisions | Consulted | Informed | Responsible |

## Pattern: Delivery vs Product Management – Avoiding the Control Trap

### Context

Modern product organizations often blur the lines between product management (prioritizing what to build and why) and delivery management (ensuring work flows smoothly, and dependencies are managed). Under pressure for predictability, Product Managers (PMs) frequently slip into project management behaviours—dictating schedules, allocating resources, and orchestrating dependencies—despite these being outside their core remit.

### Problem

When Product Managers take on delivery control, several issues arise:

- Loss of autonomy: Teams become task-driven rather than outcome-driven.

- Role confusion: Accountability for flow and outcomes becomes unclear.

- Strategic dilution: PMs spend time firefighting dependencies instead of focusing on customer value.

- Micromanagement: Leadership shifts from coaching to controlling, eroding trust and adaptability.

### Forces

- Stakeholders demand certainty and dates.

- PMs feel responsible for outcomes and timelines.

- Delivery managers may be absent or under-empowered.

- Dependencies and blockers create anxiety about delays.

### Solution – How EmergentOS Prevents the Trap

EmergentOS separates strategic prioritization from flow enablement through modular practices:

- OKRs and Lean Value Trees: Value Outcome Leads focus on defining measurable outcomes and strategic bets—not task orchestration.

- Portfolio Kanban + Flow Metrics: Delivery health and systemic blockers are visualized transparently, enabling leaders to coach through flow rather than enforce timelines.

- Team Topologies: Dependencies are managed structurally, reducing coordination overhead and cognitive load.

- Coaching-Led Governance: Leaders act as enablers, using empirical data (DORA + Flow metrics) to guide improvement—not control.

- Slowification Windows: Create space for validated discovery before High Integrity Commitments, reducing pressure for premature scheduling.

### Result

- Value Outcome Leads stay focused on value and viability, not resource juggling.

- Delivery managers optimize flow and unblock teams without imposing rigid plans.

- Teams operate with clarity and autonomy, making evidence-based commitments.

- Leadership shifts from predictive control to adaptive coaching, reinforcing trust and learning.

## Pattern: Operate Around Outcomes

### Context

Your organization is structured around projects and feature roadmaps. Teams deliver outputs but struggle to demonstrate real customer impact. Leadership wants agility but relies on centralized planning and deterministic schedules.

### Problem

Project-based models create silos, slow decision-making, and disconnect teams from customer value. Teams focus on shipping features rather than solving problems. Innovation suffers, and adaptability is low.

### Forces

- Stakeholders demand predictability and visibility.

- Teams want autonomy and purpose.

- Customers expect continuous improvement, not big-bang releases.

- Traditional governance reinforces output-driven success metrics.

### Solution

Adopt the Product Operating Model as the foundation of EmergentOS. Organize teams around customer outcomes, not projects. Empower cross-functional, stream-aligned teams to own end-to-end slices of the customer journey. Replace feature roadmaps with OKRs tied to measurable impact. Embed continuous discovery and delivery practices so learning and adaptation become routine.

### Result

Teams become outcome-focused and empowered. Delivery accelerates through iterative cycles. Customer impact is validated continuously. Leadership shifts from directing tasks to enabling strategic clarity and coaching. The organization gains adaptability without losing alignment.

### Related Patterns

- Outcome Over Output

- High Integrity Commitments

- Team Topologies

# Leadership Roles Across the Organizational Hierarchy

The roles of Value Outcome Lead (VOL), Team Outcome Lead (TOL), and Architecture Outcome Lead (AOL) are not confined to the product team level—they represent leadership patterns that scale up and down the organization. At every level, these roles form a triad of accountability for outcomes, flow, and technical integrity:

- Enterprise Level

  - VOL: CEO or Chief Product Officer (CPO) acts as the ultimate steward of business outcomes and strategic bets.

  - TOL: COO or CIO ensures operational flow across the entire organization, balancing capacity and systemic enablement.

  - AOL: CTO safeguards technical integrity and platform scalability at the enterprise level.

- Business Unit / Value Stream Level

  - VOL: Business Unit Head, Portfolio Leader, or Head of Product focuses on outcomes for a specific domain or customer segment.

  - TOL: Delivery Director or Transformation Lead optimizes flow across multiple teams and initiatives.

  - AOL: Principal Architect or Platform Lead ensures technical coherence and adaptability within the value stream.

- Team Level

  - VOL: Product Manager (or Value Outcome Lead in EmergentOS) owns customer and business outcomes for the team’s scope.

  - TOL: Delivery Manager (or Team Outcome Lead) enables smooth flow and removes impediments.

  - AOL: Tech Lead (or Architecture Outcome Lead) maintains technical quality and feasibility.

Why This Matters:

This pattern creates vertical consistency without centralization. Each level mirrors the same leadership principles—balancing value, flow, and technical integrity—while adapting scope and context. It prevents siloed decision-making and ensures that strategy, delivery, and architecture remain aligned from the C-suite to the team level.

## Connection to EDGE (Highsmith, Luu & Robinson, 2019)

EDGE advocates for adaptive portfolio governance and hypothesis-driven investment, which aligns perfectly with this triad model:

- Strategic bets and Lean Value Trees reflect the VOL’s focus on outcomes.

- Flow-based governance and portfolio Kanban reinforce the TOL’s responsibility for systemic flow.

- Technical adaptability and platform thinking echo the AOL’s role in enabling speed without sacrificing integrity.

Both Sooner Safer Happier and EDGE reject deterministic planning and emphasize empirical learning, modular practices, and coaching-led leadership. EmergentOS operationalizes these principles through its modular architecture, quarterly cadence, and coaching culture. The VOL–TOL–AOL triad becomes a scalable pattern for modern adaptive organizations, ensuring that leadership at every level reinforces outcome-driven planning, flow optimization, and technical integrity.

# Measuring What Matters with Objectives and Key Results

“OKRs surface your primary goals. They channel efforts and coordination. They link diverse operations, lending purpose and unity to the entire organization.”

— John Doerr, Measure What Matters

Objectives and Key Results (OKRs) serve as the bond between strategic intent and team execution. This alignment ensures that every product team is working toward outcomes that matter to the business and its customers.

## OKRs. What They Are

Objectives and Key Results (OKRs) are a goal-setting framework used to align teams and individuals with strategic priorities. They consist of:

- Objective: A qualitative, inspirational goal.

- Key Results: Quantifiable outcomes that measure progress toward the objective.

Example:

- Objective: Improve customer onboarding experience.

- Key Results:

  - Reduce onboarding time from 7 to 3 days.

  - Achieve 90% user satisfaction in onboarding surveys.

  - Increase onboarding completion rate to 95%.

## What OKRs Are For

OKRs are designed to:

- Align strategy with execution across teams.

- Focus effort on what matters most.

- Drive measurable outcomes, not just activity.

- Create transparency and shared understanding.

- Enable autonomy by clarifying goals without prescribing methods.

## Strengths of OKRs

| Strength | Description |
| --- | --- |
| Clarity of Purpose | Teams know why they are doing something, not just what. |
| Strategic Alignment | OKRs cascade strategy into team-level goals. |
| Outcome Focus | Shifts attention from outputs (features) to impact (results). |
| Empowerment | Teams prioritize and experiment within clear boundaries. |
| Transparency | Everyone sees what matters and how success is measured. |
| Adaptability | OKRs are reviewed and refreshed quarterly, enabling agility. |

## The Key Principles of OKRs

- Focus
 Limit OKRs to the most critical objectives to avoid dilution of effort.
 Example: Instead of 10 objectives, pick 3 that matter most for the quarter.

- Autonomy
 Teams decide how to achieve the outcomes, choosing outputs that best drive results.
 Example: Objective: Increase repeat purchases.
 Team chooses whether to build a loyalty feature or improve UX.

- Alignment
 OKRs flow from strategy → portfolio → team, ensuring coherence.
 Example: Strategic Objective: Grow retention.
 Team Objective: Increase repeat purchase rate by 15%.

- Accountability
 Make OKRs visible and measurable; review progress regularly.
 Example: Dashboard showing KR progress across teams.

- Transparency
 Share OKRs openly to foster trust and collaboration.
 Example: Publish OKRs in a shared workspace.

- Agility
 Treat OKRs as hypotheses; adapt based on learning.
 Example: If KR isn’t moving, pivot outputs or approach.

- Customer-Centricity
 Start with Who Does What By How Much to ensure OKRs reflect real behaviour change.
 Example: Existing customers (Who) increase repeat purchases (Does What) by 15% (By How Much).

- Outcome Orientation
 Key Results measure impact, not activity.
 Example: KR: Reduce churn from 10% to 5%.
 Not: Launch loyalty program by Q2.

## OKRs and Outcomes Over Outputs

OKRs are a powerful alignment tool in EmergentOS because they focus teams on outcomes, not outputs. Outputs are things we build (features, reports, campaigns), while outcomes are the changes in customer or business behaviour that indicate success.

### Jeff Gothelf & Josh Seiden’s “Who Does What by How Much” Formula

Who + Does What + By How Much

This formula ensures OKRs are outcome-focused:

- Who: The audience or user segment whose behaviour we want to influence.

- Does What: The specific behaviour we want to see.

- By How Much: The measurable change that indicates success.

Example:

- Objective: Improve customer retention.

- Key Result (using formula):

Existing customers (Who) increase repeat purchases (Does What) by 15% (By How Much).

## How to Write Good OKRs: Applying “Who Does What By How Much”

Writing effective OKRs requires clarity, focus, and a shift from outputs to outcomes. Josh Seiden and Jeff Gothelf’s formula—Who + Does What + By How Much—is a practical way to ensure Key Results measure real impact rather than activity.

### Step 1: Identify the Objective

Start with a qualitative, inspirational goal that reflects strategic intent. A good objective should be:

- Inspirational: Motivates the team.

- Qualitative: Describes an outcome, not a metric.

- Timeboxed: Achievable within the quarter.

- Specific: Clear enough to guide decisions.

Example: Improve customer onboarding experience.

### Step 2: Identify the Biggest Obstacle

Ask: “What is the biggest thing standing in the way of achieving this?”

This helps focus effort on the most critical challenge rather than spreading energy across too many fronts.

### Step 3: Define Key Results Using the Formula

For each objective, write Key Results that answer:

- Who: Which audience or user segment are we targeting?

- Does What: What specific behaviour change signals success?

- By How Much: What measurable change indicates impact?

Example:

- Objective: Improve customer onboarding experience.

- Key Result: New customers (Who) complete onboarding (Does What) within 3 days (By How Much).

Other examples:

- Existing customers increase repeat purchases by 15%.

- Support team reduces average resolution time from 48 hours to 24 hours.

### Step 4: Validate Alignment

Check that:

- Objectives inspire and clarify direction.

- Key Results measure outcomes, not outputs.

- OKRs connect to strategic priorities and are achievable within the timebox.

### Patterns to Avoid

- Output-based OKRs: e.g., “Launch feature X” (focuses on delivery, not impact).

- Vanity metrics: e.g., “Get 100 likes on a blog post” (doesn’t reflect meaningful change).

- Executive Summary	1

- Who Is This For?	3

- Disclaimer	4

- Rationale & Strategic Importance	6

- Beyond Engineering: Enterprise-Wide Applicability of EmergentOS	8

- Strategic Planning & Alignment	9

- Adaptive Budgeting & Investment	9

- Flow-Based Governance & Visibility	9

- Continuous Improvement & Capability Building	9

- Coaching-Led Governance & Leadership Development	10

- Organizational Design & Team Interaction	10

- Summary	10

- Show Me the Money!	11

- Adaptive Funding Model: Investing in Outcomes, Not Outputs	12

- 1. Strategic Framing via Lean Value Trees	12

- 2. Metered Funding via Hypothesis Validation	12

- 3. Outcome-Based Investment via OKRs	12

- 4. Flow-Based Governance via Portfolio Kanban	13

- 5. Quarterly Cadence for Funding Decisions	13

- 6. Innovation Accounting Integration	13

- Budgeting Guidance for Adaptive Funding in EmergentOS	14

- 1. Budgeting by Strategic Theme and Lean Value Tree Branches	15

- 2. Use Metered Funding Tranches	15

- 3. Tie Funding to OKRs and Outcomes	15

- 4. Enable Dynamic Reallocation	15

- 5. Support Innovation Accounting	16

- 6. Align Budgeting Cadence with EmergentOS Quarterly Cycle	16

- 7. Empower Teams with Guardrails	16

- Pattern: Outcome Over Output	17

- Context	18

- Problem	18

- Forces	18

- Solution	18

- Result	18

- Related Patterns	18

- Pattern: Legacy to Learning	19

- Context	20

- Problem	20

- Forces	20

- Solution	20

- Result	20

- Related Patterns	20

- EmergentOS Values	21

- Alignment with Simplyhealth’s Values	23

- Core Principles	25

- 1. Outcome-Driven Planning	26

- 2. Hypothesis-Driven Strategy	26

- 3. Team-Centric Autonomy	26

- 4. Flow-Based Delivery	26

- 5. Continuous Improvement	26

- 6. Engineering Excellence	27

- 7. Empirical Governance	27

- 8. Sustainable Pace and Resilience	27

- 9. Methodology Flexibility	27

- Core Domains	28

- Domain Relationships	29

- Why Flow Matters—and How EmergentOS Makes It Happen	30

- Value Stream Management in EmergentOS	32

- How EmergentOS Operationalizes VSM	33

- Why This Integration Strengthens EmergentOS	34

- Alignment with the Three Ways of DevOps	35

- 1. The First Way: Flow (Systems Thinking)	36

- 2. The Second Way: Feedback (Amplify Feedback Loops)	36

- 3. The Third Way: Continual Learning and Experimentation	36

- Alignment with Lean Thinking	37

- Output Vs Outcomes	38

- Five Signs of an Output Focused Organization	40

- EmergentOS Components	40

- Jonathan Smart’s Ways of Working Centre of Enablement	41

- Marty Cagan’s Product Operating Model  	41

- Lean Value Trees & OKRs for Strategic Alignment	41

- Team Topologies for Scalable Structure	42

- Kanban for Flow Visualization	42

- Lean Improvement Kata + Flow Engineering	42

- Engineering Best Practices + CI/CD	43

- DORA and Flow Metrics for Performance Insight	43

- EmergentOS Component Relationship Model	43

- Slowification	44

- Lean Kata & Flow Engineering	45

- Governance & Coaching	45

- Engineering Practices	45

- Pattern: Time for Reflection	46

- Context	46

- Problem	46

- Forces	46

- Solution	46

- Result	47

- Related Patterns	47

- Team Topologies	47

- Principles & Purpose	48

- Core Principles:	48

- Why It is a Good Fit for EmergentOS	48

- Team Types	48

- Interaction Modes	49

- Cross-Functional Teams	49

- Definition	49

- Principles	49

- Common Misconceptions	50

- How It Scales	50

- Strategic Impact	50

- Pattern: Team Topologies	51

- Context	52

- Problem	52

- Forces	52

- Solution	52

- Result	52

- Related Patterns	52

- Ways of Working Centre of Enablement	53

- Purpose	54

- Core Principles	54

- Interaction with Delivery Managers	55

- Interaction with Product Teams	56

- Benefits	56

- The Product Operating Model: What It Is	56

- Why It is So Successful	57

- Strategic Impact	58

- The Value Outcome Lead (fka Product Manager)	59

- Core Responsibilities	59

- What They Are Not	60

- How Value Outcome Leads Use Discovery in EmergentOS	60

- Purpose of Discovery	60

- Key Activities	60

- Continuous, Not Sequential	61

- The Team Outcome Lead	61

- Core Responsibilities	62

- Key Principles	62

- Position in the Value Stream	62

- Role in Continuous Improvement	63

- The Architecture Outcome Lead	64

- Core Responsibilities	64

- What They Are Not	65

- Why This Role Matters in EmergentOS	65

- The Role of Product Engineers in EmergentOS	65

- Core Responsibilities	65

- Why This Matters	66

- Managing Role Boundaries in EmergentOS	67

- Core Responsibilities by Role	68

- Where Overlap Happens	68

- Principles for Healthy Boundaries	69

- Practical Guardrails	69

- Pattern: Delivery vs Product Management – Avoiding the Control Trap	69

- Context	70

- Problem	70

- Forces	70

- Solution – How EmergentOS Prevents the Trap	70

- Result	71

- Pattern: Operate Around Outcomes	71

- Context	72

- Problem	72

- Forces	72

- Solution	72

- Result	72

- Related Patterns	72

- Leadership Roles Across the Organizational Hierarchy	73

- Connection to EDGE (Highsmith, Luu & Robinson, 2019)	74

- Measuring What Matters with Objectives and Key Results	75

- OKRs. What They Are	76

- What OKRs Are For	76

- Strengths of OKRs	77

- The Key Principles of OKRs	78

- OKRs and Outcomes Over Outputs	79

- Jeff Gothelf & Josh Seiden’s “Who Does What by How Much” Formula	79

- How to Write Good OKRs: Applying “Who Does What By How Much”	79

- Step 1: Identify the Objective	80

- Step 2: Identify the Biggest Obstacle	80

- Step 3: Define Key Results Using the Formula	80

- Step 4: Validate Alignment	82

- Patterns to Avoid	82

- Aspirational OKRs/Stretch Goals	82

- High Integrity Commitments	83

- How Commitments Operate in Practice	83

- Aspirational OKRs vs High Integrity Commitments	84

- Pattern: Who Does What By How Much	85

- Context	86

- Problem	86

- Forces	86

- Solution	86

- Result	87

- Pattern: High Integrity Commitments	87

- Context	88

- Problem	88

- Forces	88

- Solution	88

- Result	88

- Related Patterns	88

- Aligning Product Teams with Business Objectives	89

- Why This Works	92

- Pattern: Big Picture	92

- Context:	93

- Problem:	93

- Solution:	93

- Result:	93

- Expanding Portfolio-Level Alignment of Objectives	94

- How It Works LVTs as the Strategic Map	95

- How OKR Performance Is Rated	96

- Common Traps in OKR Implementation	97

- No-Value OKRs	98

- Low-Value OKRs	98

- How to Avoid OKR Traps	99

- Lean Value Trees: Defining Outcome-based Strategies	100

- Purpose of Lean Value Trees	101

- Structure of an LVT	101

- How LVTs Work in Practice	102

- Lean Value Trees in EmergentOS	103

- Why LVTs Matter in EmergentOS	103

- How LVTs Work in EmergentOS	103

- Example LVT	104

- Guide: Forming Strong Hypotheses in EmergentOS	105

- 1. Purpose of a Hypothesis	106

- 2. When to Form Hypotheses	106

- 3. Steps to Form a Hypothesis	106

- 4. Define Expected Outcomes	106

- 5. Validate Before Committing	107

- 6. Link to OKRs and Portfolio Kanban	108

- 7. Example	108

- Kanban: Simplicity, Flow, and Visibility	108

- Why Kanban?	109

- Portfolio-Level Kanban: Coaching Through Flow, Not Control	109

- How Leaders Use It to Coach	110

- How Kanban Supports EmergentOS	110

- How EmergentOS Aligns with Kanban	111

- Beyond the Boards	111

- Principles Alignment	111

- Running Portfolio Kanban on a Quarterly Cadence in EmergentOS	112

- How It Works	113

- Benefits	114

- How Lean Value Trees and Portfolio Kanban Work Together in EmergentOS	115

- Lean Value Trees: Define and Prioritize Value	115

- Portfolio Kanban: Manage Flow and Capacity	115

- How They Fit Together	115

- Portfolio-Level WIP Limits	116

- Why It Matters	117

- Principles	117

- Practical Guidance	117

- Common Misconceptions	117

- Pattern: Visualize Work	118

- Context	119

- Problem	119

- Forces	119

- Solution	119

- Result	119

- Related Patterns	119

- Pattern: Flow First	120

- Context	120

- Problem	120

- Forces	120

- Solution	120

- Result	120

- Related Patterns	120

- The Lean Improvement Kata & Flow Engineering	121

- What Is the Lean Improvement Kata?	122

- Role of Continuous Improvement	122

- Why It is Important for Product Delivery	122

- Flow Engineering	123

- Outcome Map	124

- Value Stream Map (Current State)	124

- Dependency Map	124

- Future State Map	124

- Flow Roadmap	124

- Flow Engineering and Kata	125

- The Flow Roadmap as OKRs	125

- Pattern: Improve Collaboratively	125

- Context	126

- Problem	126

- Forces	126

- Solution	126

- Result	126

- Related Patterns	126

- Continuous Integration (CI) & Continuous Delivery (CD)	127

- Continuous Integration (CI)	128

- Continuous Delivery (CD)	128

- Problems CI/CD Solves	130

- Why CI/CD Is Crucial for Value Outcomes	130

- How CI/CD Outperforms Legacy Practices	131

- Pattern: Deliver Continuously	132

- Context	133

- Problem	133

- Forces	133

- Solution	133

- Result	133

- Related Patterns	133

- The DORA 4 Key Metrics	134

- What Are the DORA 4 Key Metrics?	135

- Deployment Frequency	135

- Lead Time for Changes	135

- Change Failure Rate	135

- Mean Time to Recovery (MTTR)	136

- How The Metrics Arose	136

- Why DORA Metrics Drive Successful Delivery	136

- Strategic Impact in EmergentOS	137

- Pattern: Measure What Matters	137

- Context	138

- Problem	138

- Forces	138

- Solution	138

- Result	138

- Related Patterns	138

- Mik Kersten’s Flow Framework	139

- What Is the Flow Framework?	140

- The Four Flow Items	140

- Flow Items and Their Mapping to EmergentOS	141

- What Is Flow Distribution?	142

- Why It Matters:	142

- The Five Flow Metrics	143

- Flow States	144

- Measuring Value Delivery with the Flow Framework	145

- The EmergentOS – Flow Framework Synergy	145

- How Flow Metrics and DORA Metrics Work Together	146

- Integration Points	146

- Flow Metrics vs Kanban Metrics: Complementary Insights	146

- What EmergentOS Looks Like in Action	147

- Week 1–2: Strategy & Alignment	148

- Week 3–11: Discovery & Delivery	149

- Week 12: Validation & Retrospective	149

- Strategic Impact	152

- Delivery, Delivery, Delivery Vs Keeping the Lights On	154

- Understanding the Tension	155

- Strategies for Balancing Product Delivery and KTLO	155

- Governance: Purpose and Function	156

- Enablement Over Control	157

- Evidence-Based Oversight	157

- Quarterly Rhythm and Review	157

- Coaching and Maturity Support	157

- Strategic Impact of Governance	158

- Intent Based Leadership	158

- How Intent Based Leadership Works	159

- Scenario: Empowering a Stream-Aligned Product Team	159

- Context:	159

- Traditional Leadership Approach:	159

- Intent-Based Leadership Approach:	159

- Result	160

- How Intent Based Leadership Fits into EmergentOS	160

- Principles and Alignment	160

- Pattern: Coaching Culture	162

- Context	163

- Problem	163

- Forces	163

- Solution	163

- Result	163

- Related Patterns	164

- How To Adopt EmergentOS: Just Do It!	164

- The Positive Feedback Loop	166

- Maturity Model	167

- Maturity Levels	168

- Coaching Playbook	170

- Quarterly Coaching Cadence	171

- Team Maturity Coaching Tracks	171

- Foundational Teams	172

- Emerging Teams	172

- Advanced Teams	172

- Coaching Tools & Templates	173

- Coaching Rituals	174

- Coaching Success Metrics	175

- Key Competencies for Successful Implementation	176

- Strategic Alignment & Outcome Thinking	177

- Team Design & Interaction Management	177

- Flow Visualization & Delivery Management	177

- Continuous Improvement Culture	177

- Engineering Excellence	178

- Empirical Performance Measurement	178

- Hypothesis-Driven Planning	178

- Coaching & Change Enablement	179

- Summary	179

- Appendix: Agility not Agile	181

- The Four Agile Manifesto Values	182

- The 12 principles of The Agile Manifesto	183

- Mapping EmergentOS to the Agile Principles	183

- Appendix: Why EmergentOS Improves on SAFe® and Similar Models	185

- The Problem with Determinism, Predictive Scheduling, and Estimation	186

- Estimation Accuracy Is Fundamentally Unreliable	186

- Different Estimates Create Different Projects	186

- No Universal Estimation Technique Works Across Contexts	186

- Strategic Implications	187

- Why Outcome-Driven, Empirical Delivery Is Better	187

- Head-to-Head Comparison	187

- Appendix: Patterns	188

- Pattern: Big Picture	189

- Pattern: Coaching Culture	189

- Pattern: Deliver Continuously	189

- Pattern: Delivery vs Product Management – Avoiding the Control Trap	189

- Pattern: Flow First	189

- Pattern: High Integrity Commitments	189

- Pattern: Legacy to Learning	190

- Pattern: Measure What Matters	190

- Pattern: Operate Around Outcomes	190

- Pattern: Outcome Over Output	190

- Pattern: Team Topologies	190

- Pattern: Who Does What By How Much	191

- Pattern: Visualize Work	191

- Glossary	192

## Aspirational OKRs/Stretch Goals

A stretch goal, often referred to as a moon shot, is an ambitious, aspirational objective that intentionally pushes a team beyond its comfort zone. It is designed to challenge assumptions, encourage innovation, and drive significant improvement or transformation. Stretch goals are often set with the understanding that full achievement may not be guaranteed—but the pursuit itself leads to valuable learning and progress.

In the context of OKRs, stretch goals are typically reflected in aspirational objectives with aggressive key results. Scoring 0.6 or 0.7 on a stretch OKR is considered a success, because it means meaningful progress was made toward a bold target.

Note: ‘Stretch goals’ in the OKR framework are aspirational objectives designed to push teams beyond their comfort zone and encourage innovation—even if full achievement is unlikely. This is fundamentally different from SAFe’s interpretation of ‘stretch goals,’ which are not aspirational but rather represent overflow work—additional planned items that may be tackled if the team completes its committed objectives early. These goals exist to fill perceived spare capacity and are a byproduct of deterministic, capacity-based planning, not a mechanism for ambition or learning.

## High Integrity Commitments

High Integrity Commitments are a core concept in Product Operating Model and therefore, by extension, this operating system. They represent a team’s explicit, confident commitment to deliver a specific outcome or capability—based on validated discovery, technical feasibility, and alignment with strategic goals.

Unlike traditional delivery promises based on estimates or roadmaps, High Integrity Commitments are made only when teams have sufficient evidence to believe they can deliver with high confidence and integrity. However, teams are expected to score 1.0 for each High Integrity Commitment, i.e. they are expected to deliver the requested outcomes in full.

### How Commitments Operate in Practice

- Teams begin with discovery work (e.g. spikes, prototypes, user testing) to validate the problem, solution, and feasibility.

- Once confident, they make a commitment to deliver—not just a feature, but a meaningful outcome.

- These commitments are time-bound, visible, and tracked through delivery and validation.

- Leadership supports teams by removing blockers, not micromanaging execution.

Example: A team might commit to reducing onboarding time by 50% within the quarter, based on validated user insights and a tested technical approach.

High Integrity Commitments align perfectly with EOS’s emphasis on:

- Outcome-driven planning: Commitments are tied to OKRs and customer impact.

- Empirical delivery: Teams validate feasibility before committing.

- Autonomy and trust: Teams own their commitments and are empowered to deliver.

- Flow and visibility: Commitments are tracked via Kanban boards and validated through telemetry.

They replace estimation-heavy deterministic planning with evidence-based confidence, reinforcing EOS’s shift from predictability to adaptability.

## Aspirational OKRs vs High Integrity Commitments

Aspirational OKRs/Stretch goals differ from High Integrity Commitments, which are delivery promises made with high confidence based on validated discovery and feasibility. While stretch goals inspire ambition, High Integrity Commitments ensure reliability and trust in execution.

Aspirational OKRs might include goals like “Double user engagement” or “Launch in three new markets”—ambitious, directional, and motivating.

High Integrity Commitments are made only after discovery and validation, such as “Deliver onboarding flow that reduces time-to-value by 50%”—with strong confidence in execution.

| Aspect | Aspirational OKRs | High Integrity Commitments |
| --- | --- | --- |
| Purpose | Drive innovation and bold change | Deliver a validated, feasible outcome |
| Confidence Level | Low to medium (ambitious by design) | High (based on discovery and feasibility) |
| Risk Tolerance | High – failure is acceptable | Low – failure should be rare |
| Measurement | Partial achievement is expected | Full delivery is expected |
| Use Case | Inspire teams to push boundaries | Align stakeholders on dependable delivery |

Together, stretch goals and high integrity commitments balance ambition and accountability, enabling teams to innovate while maintaining trust with stakeholders.

## Pattern: Who Does What By How Much

### Context

Organizations want to align teams around measurable outcomes, not just outputs. OKRs are adopted as a goal-setting framework, but many teams struggle to write OKRs that clearly express impact. Objectives often become vague aspirations, and Key Results drift into task lists or vanity metrics.

### Problem

- OKRs are written as outputs (e.g., “Launch feature X”) rather than outcomes.

- Key Results lack clarity on who is affected, what behaviour changes, and by how much.

- Teams find it hard to connect OKRs to strategic priorities and customer impact.

### Forces

- Stakeholders demand visibility and measurable progress.

- Teams want autonomy but need clarity on what success looks like.

- Pressure to deliver quickly leads to output-focused goals.

- Measuring behavioural change feels harder than tracking delivery milestones.

### Solution

Apply Seiden & Gothelf’s formula: Who + Does What + By How Much to craft outcome-focused Key Results.

- Start with a strong Objective: Inspirational, qualitative, timeboxed, and specific.

- Identify the biggest obstacle: What’s preventing success? This sharpens focus.

- Write Key Results using the formula:

  - Who: Define the audience or user segment.

  - Does What: Specify the behaviour or action that signals success.

  - By How Much: Quantify the change that matters.

- Validate alignment: Ensure OKRs reflect strategic priorities and are achievable within the timebox.

Example

- Objective: Improve customer onboarding experience.

- Key Result: New customers (Who) complete onboarding (Does What) within 3 days (By How Much).

### Result

- OKRs become outcome-driven and measurable.

- Teams gain clarity on what success looks like and why it matters.

- Leadership shifts from controlling outputs to enabling impact.

- Progress is tracked through meaningful behavioural and business changes, not feature delivery.

## Pattern: High Integrity Commitments

### Context

Your organization needs confidence in delivery for critical outcomes, but traditional commitments are based on estimates and assumptions. Teams often overpromise and underdeliver, eroding trust and creating tension between stakeholders and delivery teams.

### Problem

Deterministic planning forces teams to commit before uncertainty is resolved. This leads to missed deadlines, compromised quality, and reactive firefighting. Stakeholders lose trust, and teams feel pressured to guess rather than learn.

### Forces

- Stakeholders want certainty for high-priority initiatives.

- Teams need time to validate feasibility and reduce risk.

- Pressure to commit early undermines experimentation and learning.

- Failure to deliver damages credibility and morale.

### Solution

Introduce High Integrity Commitments as a practice within EmergentOS. Teams make commitments only after validated discovery and technical feasibility checks. These commitments are tied to outcomes, not outputs, and are supported by evidence from prototypes, spikes, and telemetry. Leadership enables this by creating space for Slowification—time for practice and learning before execution.

### Result

Commitments become reliable and meaningful. Stakeholders gain confidence without sacrificing adaptability. Teams deliver with integrity, knowing they have validated assumptions and reduced uncertainty. Trust grows, and planning shifts from guesswork to evidence-based confidence.

### Related Patterns

- Outcome Over Output

- Time for Reflection

- Coaching Culture

## Aligning Product Teams with Business Objectives

Company-Level Strategy
Leadership defines high-level strategic objectives—often focused on growth, customer satisfaction, innovation, or operational efficiency.

Portfolio-Level Outcome Mapping and Lean Value Trees
Strategic goals are translated into portfolio-level outcomes using Strategic Outcome Mapping and visualized in Lean Value Trees (LVTs). LVTs break down strategic themes into bets, value streams, and initiatives, ensuring every investment is tied to measurable outcomes. This provides the strategic map that feeds into Portfolio Kanban for flow-based governance.

Strategic Outcome Mapping: Defining Problems Worth Solving
Strategic Outcome Mapping is a collaborative technique used to translate strategic goals into actionable outcomes. It helps teams shift from feature delivery to impact-driven planning by identifying:

- Target outcomes: What measurable change do we want to see?

- Customer behaviours: What actions or patterns need to change?

- Problems worth solving: What is preventing those behaviours today?

- Experiments and initiatives: What can we try to influence those outcomes

Product leadership facilitates Strategic Outcome Mapping sessions during the Slowification window (Weeks 1–2) to ensure teams are solving the right problems—not just building features. These sessions often use visual canvases to align teams around shared goals, clarify assumptions, and prioritize work based on strategic impact.

How It Connects to LVTs and Portfolio Kanban

- Outcome Mapping informs the hypotheses and expected outcomes that populate LVT branches.

- Prioritized initiatives from LVTs move into Portfolio Kanban for flow-based governance and capacity planning.

- Portfolio Kanban visualizes initiative flow across stages (Funnel → Review → Analysis → Ready → Committed → In Progress → Done), enabling leaders to coach through flow—not control through timelines.

Team-Level OKRs
Product teams define OKRs that cascade from LVT branches, ensuring relevance and alignment. Each team’s objectives reflect their unique contribution to the broader strategy and are linked to hypotheses validated through discovery.

Continuous Review & Feedback
OKRs are reviewed weekly alongside team Kanban boards and Portfolio Kanban, supported by flow metrics and DORA indicators. Quarterly retrospectives and outcome reviews ensure strategic learning feeds back into planning and updates LVTs for the next cycle.

### Why This Works

- Strategic Clarity: LVTs and Outcome Mapping make the link between company goals and team initiatives explicit.

- Autonomy with Alignment: Teams choose how to achieve outcomes, not just what to build.

- Prioritization: OKRs and LVTs help teams focus on what matters most, reducing noise and reactive work.

- Evidence-Based Planning: Hypotheses and OKRs are validated through telemetry and customer feedback—not just delivery milestones.

## Pattern: Big Picture

### Context:

Organizations often struggle to connect day-to-day delivery work with strategic objectives. Teams focus on features or tasks without understanding how their efforts contribute to customer impact or business goals.

### Problem:

Without a shared “big picture,” teams operate in silos. Strategic intent gets lost in translation, leading to misaligned priorities, wasted effort, and difficulty demonstrating value.

### Solution:

Use Strategic Outcome Mapping and Lean Value Trees (LVTs) to create a visual, collaborative representation of how strategic goals cascade into measurable outcomes and team-level objectives.

This mapping clarifies:

- Why the work matters (strategic intent)

- What problems are worth solving (customer and business outcomes)

- How initiatives and experiments connect to those outcomes

Lean Value Trees provide the strategic hierarchy:

- Strategic Themes → Bets → Value Streams → Initiatives → OKRs

Prioritized initiatives from LVTs then move into Portfolio Kanban, which visualizes flow across stages and enables leaders to coach through flow—not control through timelines.

Outcome Mapping and LVT sessions typically occur during the Slowification window (Weeks 1–2) and feed directly into OKR planning and Portfolio Kanban setup.

### Result:

Teams gain clarity on the big picture, align their OKRs with strategic outcomes, and prioritize work that delivers measurable impact. Leadership shifts from prescribing features to enabling hypothesis-driven, outcome-focused decisions.

Portfolio Kanban ensures systemic visibility and adaptability, while LVTs maintain strategic coherence across the portfolio.

## Expanding Portfolio-Level Alignment of Objectives

EmergentOS simplifies portfolio-level alignment by operationalizing strategic intent through modular practices like Lean Value Trees (LVTs), OKRs, Strategic Outcome Mapping, and Portfolio Kanban. These tools ensure that every initiative, team, and experiment is connected to shared objectives—without relying on centralized control or heavyweight planning.

### How It Works LVTs as the Strategic Map

At the portfolio level, leadership defines high-level strategic objectives, which are visualized in Lean Value Trees. LVTs break down strategic themes into bets, value streams, and initiatives, ensuring every investment is tied to measurable outcomes.

Strategic Outcome Mapping

Outcome Mapping identifies:

- Problems worth solving

- Customer behaviours to influence

- Experiments needed to validate assumptions

These insights populate LVT branches and cascade into team-level OKRs, ensuring relevance and alignment across the organization.

Portfolio Kanban for Flow-Based Governance

Portfolio Kanban provides a visual dashboard of work in progress across streams. It shows:

- Which initiatives align with LVT branches and OKRs

- Where flow is blocked

- How dependencies are managed

Leaders use this visibility to coach through flow—not control through timelines, guiding prioritization, spotting systemic bottlenecks, and facilitating strategic conversations.

Practical Steps

- Facilitate quarterly Outcome Mapping and LVT sessions to define shared goals.

- Use visual canvases to align teams around customer outcomes and hypotheses.

- Cascade OKRs from LVT branches to team-level objectives.

- Link work items in Portfolio Kanban to specific OKRs and hypotheses.

- Review flow metrics and outcome progress weekly to adapt and learn.

Benefits

- Strategic Clarity: LVTs and OKRs make the link between company goals and team initiatives explicit.

- Autonomy with Alignment: Teams choose how to achieve outcomes, not just what to build.

- Evidence-Based Prioritization: Work is guided by validated hypotheses and impact—not assumptions.

- Continuous Learning: Quarterly reviews feed insights back into strategy and update LVTs.

By embedding these practices, EmergentOS enables scalable alignment without sacrificing speed, autonomy, or adaptability.

## How OKR Performance Is Rated

OKRs are reviewed at the end of the quarterly cycle and scored based on how much progress was made toward each Key Result. A common rating scale is:

- 0.0 – 0.3: Little progress; objective not achieved.

- 0.4 – 0.6: Moderate progress; partial achievement.

- 0.7 – 1.0: Strong progress; objective achieved or exceeded.

Importantly, OKRs are not performance evaluations. They are learning tools—used to reflect on what was attempted, what worked, and what needs to change. A score of 0.6 might be perfectly acceptable for a stretch goal, especially if valuable insights were gained.

## Common Traps in OKR Implementation

1. Too Many Objectives

- Trap: Overloading teams with too many goals dilutes focus.

- Fix: Limit to 3–5 objectives per cycle, each with no more than 5 key results.

2. Vague or Unmeasurable Key Results

- Trap: Key results that are subjective or unclear make progress hard to track.

- Fix: Ensure KRs are specific, time-bound, and measurable. Completion of all KRs should clearly indicate the objective is achieved.

3. Confusing Outputs with Outcomes

- Trap: Focusing only on deliverables (outputs) rather than impact (outcomes).

- Fix: Include both input and output metrics but prioritize results that reflect real progress toward the objective.

4. Linking OKRs to Compensation

- Trap: Tying OKRs to bonuses or performance reviews encourages sandbagging and risk aversion.

- Fix: Keep OKRs separate from compensation to foster stretch goals and honest progress tracking.

5. Top-Down Only Goal Setting

- Trap: Imposing OKRs from leadership without team input reduces buy-in.

- Fix: Use a mix of top-down and bottom-up planning to ensure alignment and ownership.

6. Ignoring Regular Check-Ins

- Trap: Setting OKRs and forgetting them until the end of the cycle.

- Fix: Hold regular conversations to review progress, adjust course, and give feedback.

7. No Distinction Between Committed and Aspirational Goals

- Trap: Treating all OKRs as equal leads to confusion and missed expectations.

- Fix: Clearly label committed goals (must be achieved) vs. aspirational goals (stretch targets).

### No-Value OKRs

These OKRs do not drive any meaningful change. They often reflect:

- Business-as-usual tasks (e.g. “Attend weekly team meetings”)

- Vanity metrics (e.g. “Get 100 likes on a blog post”)

- Unmeasurable aspirations (e.g. “Be more innovative”)

Why they fail:

- They do not challenge the team or move the needle.

- They are often disconnected from strategic priorities.

- They lack observable outcomes or impact.

### Low-Value OKRs

These OKRs have some merit but fall short of strategic relevance or clarity. Common signs:

- Too tactical (e.g. “Fix 10 bugs” without linking to customer satisfaction or velocity)

- Misaligned with business outcomes (e.g. “Launch feature X” without defining success)

- Poorly scoped (e.g. “Improve performance” — how much, for whom, and why?)

Why they underperform:

- They do not inspire or guide decision-making.

- They are hard to prioritize against competing work.

- They do not help teams understand trade-offs or value creation.

### How to Avoid OKR Traps

1. Tie Objectives to Strategic Outcomes

- Ask: “If we achieve this, what will be different for the business or customer?”

- Use verbs like increase, reduce, improve, accelerate — paired with impact.

2. Design Key Results as Evidence of Success

- Make them quantifiable, time-bound, and outcome-oriented.

- Example: Instead of “Improve onboarding,” use “Reduce average onboarding time from 7 to 3 days.”

3. Use the “So What?” Test

- For each KR, ask: “So what if we hit this?”

- If the answer is unclear or trivial, it is likely to be of low value.

4. Map OKRs to Value Streams or Customer Impact

- Ensure every OKR has a clear line of sight to user behaviour, business metrics, or team capabilities.

5. Review and Refine Collaboratively

- Use peer reviews or OKR calibration sessions to challenge assumptions and surface hidden misalignments.

# Lean Value Trees: Defining Outcome-based Strategies

Lean Value Trees (LVTs) were introduced by Linda Luu, Jim Highsmith, and Dave Robinson as part of Thoughtworks’ work on value-driven transformation. The concept was first published in their book Edge: Value-Driven Digital Transformation to help organizations connect strategy to execution through lightweight, hypothesis-driven portfolio governance.

LVTs are a strategic tool for connecting business objectives to delivery work in a clear, outcome-driven way. They provide a structured, visual representation of how high-level goals break down into actionable initiatives, ensuring that every piece of work contributes to measurable value.

## Purpose of Lean Value Trees

- Align Strategy and Execution: LVTs make the link between strategic themes and delivery initiatives explicit.

- Enable Prioritization: By showing the hierarchy of objectives and their expected value, LVTs help organizations decide where to invest.

- Support Adaptability: Unlike rigid roadmaps, LVTs allow for continuous reprioritization as new insights emerge.

## Structure of an LVT

- Vision (Optional Top Layer)
The long-term aspiration or purpose of the organization.

- Strategic Themes (or Strategic Goals)
High-level business objectives or OKRs that define the organization’s direction.

- Bets
Hypotheses about where to invest to achieve those goals.

- Bets are strategic experiments—they assume that if we invest in this area, we will move closer to the goal.

- Each bet should have a clear hypothesis and measurable success criteria.

- Value Streams
Major areas of investment that deliver value to customers and the business.

(Sometimes Bets and Value Streams overlap, but typically Bets are more hypothesis-driven, while Value Streams are structural.)

- Initiatives/Epics
Large bodies of work that support the bets and value streams. These are the actionable elements that teams will eventually deliver.

- Hypotheses and Outcomes
Statements of expected impact for each initiative, validated through delivery and measurement.

## How LVTs Work in Practice

- Step 1: Define Strategic Themes
Start with the organization’s top-level objectives (e.g., increase customer retention by 10%).

- Step 2: Identify Value Streams
Group related products or services that deliver value toward those objectives.

- Step 3: Break Down into Initiatives
Define initiatives or epics that will help achieve the outcomes.

- Step 4: Link to Metrics and OKRs
Attach measurable outcomes to each initiative to ensure accountability.

- Step 5: Feed into Portfolio Kanban
Prioritized initiatives from the LVT move into the Portfolio Kanban system for flow-based governance and capacity planning.

Result: LVTs provide the strategic map, while Portfolio Kanban provides the execution engine, ensuring that work is both aligned and manageable.

## Lean Value Trees in EmergentOS

EmergentOS uses LVTs as a strategic alignment tool to ensure that every initiative in the portfolio is connected to measurable business outcomes. LVTs provide the strategic map, while Portfolio Kanban provides the execution engine.

### Why LVTs Matter in EmergentOS

- Strategic Clarity: LVTs break down high-level business objectives into value streams, initiatives, and hypotheses, making the link between strategy and delivery explicit.

- Outcome Orientation: Each branch of the tree ties work to measurable outcomes, reinforcing EmergentOS’s principle of focusing on outcomes over output.

- Adaptability: Unlike static roadmaps, LVTs allow for continuous reprioritization as new insights emerge during quarterly cycles.

### How LVTs Work in EmergentOS

- Start with Strategic Themes: Use OKRs to define the organization’s top-level objectives.

- Identify Value Streams: Group related products or services that deliver value toward those objectives.

- Break Down into Initiatives: Define initiatives or epics that will help achieve the outcomes.

- Attach Hypotheses and Metrics: Each initiative includes a hypothesis and measurable success criteria as defined by one or more team-level OKRs.

- Feed into Portfolio Kanban: Prioritized initiatives from the LVT move into the Portfolio Kanban system for flow-based governance and capacity planning.

Result: LVTs ensure that EmergentOS operates as a strategy-to-execution system, where every piece of work is traceable to business value and managed through flow-based governance.

## Example LVT

# Guide: Forming Strong Hypotheses in EmergentOS

## 1. Purpose of a Hypothesis

A hypothesis is a testable assumption that links an action (initiative) to an expected outcome. It answers:

“If we do X, then Y will happen, because Z.”

## 2. When to Form Hypotheses

- During Slowification windows (Weeks 1–2 and Week 12).

- After Strategic Outcome Mapping and before committing to initiatives.

- Before adding initiatives to Portfolio Kanban.

## 3. Steps to Form a Hypothesis

Step 1: Start with the Strategic Theme
Example: Improve customer retention by 10% this quarter.

Step 2: Identify the Problem or Opportunity
Use discovery insights: Users drop off during onboarding after step 3.

Step 3: Frame the Hypothesis
Use the template:

If we [action], then [measurable outcome], because [reason].

Example:

If we reduce onboarding steps from 5 to 3, then completion rates will increase by 30%, because friction is the main cause of drop-off.

## 4. Define Expected Outcomes

- Baseline: Current metric (e.g., 60% onboarding completion).

- Target: Desired change (e.g., 90% completion).

- Timeframe: When you expect to see the change (e.g., within 3 months).

- Confidence Level: High / Medium / Low (based on evidence).

## 5. Validate Before Committing

- Run experiments (spikes, prototypes, A/B tests) during Slowification.

- Gather data to confirm or adjust the hypothesis.

- Only make High Integrity Commitments after validation.

## 6. Link to OKRs and Portfolio Kanban

- Attach the hypothesis to the relevant LVT branch.

- Ensure OKRs reflect the expected outcome.

- Add the initiative to Portfolio Kanban for flow-based governance.

## 7. Example

Strategic Theme: Improve Customer Retention

Hypothesis:

If we introduce a guided onboarding tutorial, then onboarding completion will increase by 20%, because users currently abandon the process due to lack of clarity.

Expected Outcome:

- Completion rate: 60% → 80%

- Confidence: Medium (based on usability tests)

Linked OKR:

- Objective: Improve onboarding experience

- Key Result: Increase onboarding completion to 80%

This approach ensures hypotheses are evidence-informed, testable, and aligned with strategic outcomes.

# Kanban: Simplicity, Flow, and Visibility

Kanban is a lightweight, visual method for managing work that emphasizes flow, focus, and continuous improvement. In this operating system, Kanban is used at both the team and portfolio levels to make work visible, reduce friction, and guide delivery with real-time insight.

## Why Kanban?

Simplicity

- Kanban is easy to adopt and does not require changing existing roles or ceremonies.

- Teams can start with what they do today and evolve their process incrementally.

Focus on Flow

- Work is visualized as it moves through stages (e.g. discovery → delivery → validation).

- Work-in-progress (WIP) limits help teams avoid overload and maintain steady throughput.

- Flow metrics (e.g. cycle time, lead time, throughput) provide actionable feedback.

Making Work Visible

- Kanban boards expose hidden work, blockers, and bottlenecks.

- Everyone—from engineers to executives—can see what is in progress, what is stuck, and what is next.

- This transparency fosters better conversations, prioritization, and accountability.

Pull-Based System

- Kanban operates as a pull system, meaning teams only start new work when they have capacity.

- This prevents overloading individuals or teams and encourages just-in-time delivery.

- Pull systems promote flow efficiency by reducing context switching and idle work.

## Portfolio-Level Kanban: Coaching Through Flow, Not Control

While team-level Kanban boards visualize discovery, delivery, and improvement work, portfolio-level Kanban provides a strategic view of flow across multiple teams and initiatives. It is not a tool for enforcing deadlines—it is a tool for enabling evidence-based coaching, alignment, and systemic improvement.

What It Shows

- Work in progress across streams: Initiatives, experiments, and outcomes mapped to OKRs.

- Flow health: Bottlenecks, blockers, and aging work items.

- Dependency visibility: Cross-team interactions and service relationships.

- Outcome alignment: Which work contributes to strategic goals and which does not.

## How Leaders Use It to Coach

Guide Prioritization

- Leaders help teams focus on high-impact work by reviewing which items align with OKRs.

- They ask: “Is this work contributing to a validated outcome?”

Spot Systemic Bottlenecks

- Instead of escalating delays, leaders use flow metrics to diagnose root causes.

- They ask: “Why is this item aging? Is it blocked by unclear ownership or technical debt?”

Enable Autonomy

- Leaders avoid micromanagement by trusting teams to manage their own flow.

- They coach teams to self-identify blockers and run improvement experiments.

Facilitate Strategic Conversations

- Portfolio Kanban becomes a shared language for product, engineering, and leadership.

- It supports quarterly reviews, OKR planning, and strategy refreshes.

## How Kanban Supports EmergentOS

Aligns with OKRs
Teams can link work items to key results, ensuring alignment with outcomes.

Enables Lean Kata
Flow metrics from Kanban boards inform improvement experiments.

Supports Autonomy
Teams manage their own flow, reducing reliance on centralized planning.

Scales Easily
Portfolio Kanban boards provide visibility across teams without heavyweight governance.

## How EmergentOS Aligns with Kanban

EmergentOS (EOS) operationalizes Kanban’s philosophy across strategy, governance, and delivery—not just as a workflow tool. It scales Kanban’s principles into an organizational operating system.

### Beyond the Boards

EOS applies Kanban thinking at every level:

- Strategic: LVTs, OKRs and outcome mapping visualize priorities and align flow with business goals.

- Portfolio: Portfolio Kanban provides systemic visibility and coaching opportunities.

- Operational: Flow metrics and improvement OKRs ensure delivery health and adaptability.

### Principles Alignment

Start with what you do now

- EmergentOS is modular and composable, allowing teams to adopt practices incrementally without a big-bang transformation.

- It encourages evolutionary change through Lean Kata and Flow Engineering, not wholesale disruption.

Respect current roles and responsibilities

- It does not mandate new roles or ceremonies like some scaled frameworks.

- Leadership shifts to a coaching role rather than imposing structural upheaval.

Encourage acts of leadership at all levels

- Intent-Based Leadership and coaching culture empower teams and individuals to make decisions and lead improvements.

- Continuous improvement is everyone’s responsibility, embedded in the quarterly cadence.

| Kanban Principle | How EmergentOS Delivers It |
| --- | --- |
| Visualize Work | Portfolio and team-level Kanban boards make delivery and improvement work visible. |
| Limit Work in Progress (WIP) | Flow-based delivery and WIP limits are core to managing throughput and reducing overload. |
| Manage Flow | Flow metrics (cycle time, throughput) and DORA metrics guide coaching and improvement. |
| Make Policies Explicit | OKRs, High Integrity Commitments, and governance rituals clarify priorities and decision-making rules. |
| Implement Feedback Loops | Weekly flow reviews, quarterly retrospectives, and telemetry-driven validation embed feedback at multiple levels. |
| Improve Collaboratively, Evolve Experimentally | Lean Kata and Flow Engineering institutionalize small, data-driven experiments for continuous improvement. |

## Running Portfolio Kanban on a Quarterly Cadence in EmergentOS

Portfolio Kanban in EmergentOS provides a lightweight governance mechanism for aligning strategic initiatives with organizational capacity—without reverting to rigid, deterministic planning. When combined with the quarterly cadence, it ensures predictability, transparency, and flow across all value streams.

### How It Works

- Visualize the Portfolio
A Portfolio Kanban board represents the lifecycle of strategic initiatives, typically using stages such as:

Funnel → Review → Analysis → Ready for Planning → Committed → In Progress → Done.

Each card represents a large initiative or epic, not individual tasks.

- Plan Ahead for the Next Quarter

  - During the Slowification window (Weeks 1–2 of the current quarter), initiatives in the Funnel and Review stages are assessed using Strategic Outcome Mapping and OKRs.

  - High-priority initiatives move into Ready for Planning, where dependencies and capacity needs are identified.

  - These initiatives are being shaped for the next quarter, not the current one, ensuring shared services like Infrastructure and Security have advance visibility.

- Commit at the Start of the Next Quarter

  - By the start of the next quarter, previously prepared initiatives move into Committed, forming the basis of the quarterly plan.

  - This approach avoids wasted effort on work that may not start immediately while preserving flexibility.

- Manage Load with WIP Limits

  - Apply Work-in-Progress (WIP) limits at the Committed and In Progress stages to prevent overloading teams and shared services.

  - This ensures enabling teams can plan capacity and avoid last-minute surprises.

- Make Dependencies Visible

  - Use tags, swim lanes, or dependency markers to highlight initiatives requiring cross-team support.

  - This transparency allows proactive coordination and reduces bottlenecks.

- Continuous Review and Adaptation

  - Conduct Portfolio Sync sessions (bi-weekly or monthly) to monitor flow, address blockers, and adjust priorities based on real-time data.

  - If urgent work emerges, decisions to defer or swap initiatives are made using capacity signals from the board.

### Benefits

- Predictability without rigidity: Teams know what is likely coming next while retaining flexibility to adapt.

- Load balancing: WIP limits prevent systemic overload and protect shared services.

- Transparency: Everyone sees the big picture, reducing hidden work and unplanned escalations.

Result: Portfolio Kanban turns strategy into a living system, enabling EmergentOS to balance strategic alignment with operational flow.

## How Lean Value Trees and Portfolio Kanban Work Together in EmergentOS

EmergentOS uses Lean Value Trees (LVTs) and Portfolio Kanban as complementary practices to connect strategy to execution while maintaining adaptability and flow.

### Lean Value Trees: Define and Prioritize Value

- LVTs break strategic themes into value streams, then into initiatives and epics, showing how each contributes to business outcomes.

- They provide context and prioritization logic—why we are doing something and what value it delivers.

- This ensures that every initiative is tied to measurable outcomes, not just output.

### Portfolio Kanban: Manage Flow and Capacity

- Portfolio Kanban takes those prioritized initiatives from the LVT and visualizes their flow through stages such as:

Funnel → Review → Analysis → Ready for Planning → Committed → In Progress → Done.

- It applies WIP limits to manage organizational load, makes dependencies visible, and ensures shared services (e.g., Infrastructure, Security) are not overwhelmed.

- This turns strategy into a living system, where work is continuously prioritized and adapted based on real-time data.

## How They Fit Together

- LVT answers: “What should we do and why?”

- Portfolio Kanban answers: “How do we manage and deliver it effectively?”

- In practice:

  - Use LVTs during the Slowification window to identify and prioritize initiatives for the next quarter.

  - Feed those initiatives into Portfolio Kanban for flow-based governance and capacity planning.

Result: EmergentOS combines the strategic clarity of Lean Value Trees with the operational discipline of Portfolio Kanban, enabling organizations to align around outcomes while maintaining adaptability and flow.

## Portfolio-Level WIP Limits

A Portfolio WIP Limit is a cap on the number of active initiatives across the organization or within a value stream. It ensures that work flows predictably and outcomes are delivered faster by reducing systemic overload.

### Why It Matters

- Flow Efficiency: Starting fewer initiatives accelerates completion and value delivery.

- Strategic Focus: Forces prioritization of the most impactful work.

- Predictability: Reduces variability and improves forecasting.

- Risk Reduction: Avoids spreading resources too thin, which increases failure risk.

### Principles

- Start Less, Finish More
Limit active initiatives to match organizational capacity and complexity.

- Apply WIP Limits at Every Level

  - Team Level: Limit stories/tasks in progress.

  - Value Stream Level: Limit active features/epics.

  - Portfolio Level: Limit initiatives across streams.

- Visualize Work
Use Portfolio Kanban to make WIP visible and enforce limits.

- Prioritize Ruthlessly
Only start initiatives that align with strategic outcomes and OKRs.

### Practical Guidance

- Set Limits Based on Capacity:
Example: If a value stream has 4 stream-aligned teams, cap at 2–3 initiatives to avoid splitting focus.

- Use Explicit Policies:
Define what counts as “in progress” (e.g., funded and staffed).

- Review Regularly:
Adjust limits as capacity or strategic priorities change.

### Common Misconceptions

- Myth: More initiatives = faster delivery.
Reality: More initiatives = slower flow and delayed outcomes.

- Myth: WIP limits only apply to teams.
Reality: System-level WIP limits prevent organizational overload.

## Pattern: Visualize Work

### Context

Teams and leaders struggle to understand what is in progress, what is blocked, and what is next. Work is hidden in spreadsheets, status reports, or siloed tools. Conversations focus on deadlines rather than flow, and improvement opportunities remain invisible.

### Problem

Without visibility, teams lose focus and alignment. Bottlenecks go unnoticed; dependencies cause delays, and leadership resorts to micromanagement for control. Transparency is low; trust erodes, and predictability suffers.

### Forces

- Stakeholders want clarity and progress updates.

- Teams need autonomy but fear being blindsided by hidden work.

- Leaders want to manage risk without adding overhead.

- Existing reporting systems are static and outdated.

### Solution

Make work visible using Kanban boards at both team and portfolio levels. Visualize discovery, delivery, and improvement tracks. Apply WIP limits to prevent overload and highlight flow health. Use flow metrics (cycle time, throughput, aging work) to guide conversations. Portfolio Kanban provides systemic visibility, enabling leaders to coach through flow—not control through timelines.

### Result

Transparency improves alignment and trust. Teams gain clarity on priorities and blockers. Leaders shift from enforcing deadlines to enabling flow. Conversations become evidence-based, focusing on outcomes and improvement rather than status reporting.

### Related Patterns

- Flow First

- Improve Collaboratively

- Outcome Over Output

- Coaching Culture

## Pattern: Flow First

### Context

Your organization struggles with delays, bottlenecks, and unpredictable delivery. Teams are busy, but work piles up in queues, dependencies stall progress, and leadership focuses on deadlines rather than throughput.

### Problem

Traditional planning emphasizes scope and dates, not flow. Work starts before teams have capacity, creating overload and context switching. Bottlenecks remain hidden, and improvement is reactive rather than systemic.

### Forces

- Stakeholders want visibility and predictability.

- Teams feel pressure to start more work to “look busy.”

- Dependencies and handoffs slow progress.

- Metrics often measure output, not flow health.

### Solution

Make flow the primary lens for planning and governance. Visualize work using Kanban at team and portfolio levels. Apply WIP limits to prevent overload. Use flow metrics (cycle time, throughput, aging work) and DORA indicators to guide decisions. Embed Lean Kata and Flow Engineering to continuously improve delivery systems. Coach leaders to manage through flow—not control through timelines.

### Result

Work moves predictably and smoothly. Bottlenecks are surfaced and addressed early. Teams deliver iteratively without burnout. Leadership gains real-time insight into delivery health and focuses on enabling flow rather than enforcing deadlines.

### Related Patterns

- Visualize Work

- Improve Collaboratively

- Outcome Over Output

- Coaching Culture

# The Lean Improvement Kata & Flow Engineering

## What Is the Lean Improvement Kata?

The Lean Improvement Kata is a structured routine for continuous improvement. Originating from Toyota’s lean practices, it guides teams through a cycle of:

- Understanding the current condition

- Setting a target condition

- Identifying obstacles

- Running small experiments to move toward the target

It is not a one-time activity—it is a habitual learning loop that helps teams improve how they work, not just what they deliver.

## Role of Continuous Improvement

Lean Kata is embedded in the delivery rhythm to:

- Diagnose bottlenecks in flow or collaboration

- Run experiments to improve speed, quality, or autonomy

- Reflect and adapt based on real outcomes

In this operating system, teams run quarterly Kata cycles alongside delivery work, often targeting areas like lead time reduction, handoff minimization, or flow efficiency.

## Why It is Important for Product Delivery

While delivering features is essential, product teams that focus solely on output risk missing the deeper goal: creating meaningful customer and business outcomes. Continuous improvement empowers teams to refine how they work, not just what they build—leading to faster flow, better quality, and more impactful solutions. By regularly inspecting delivery processes, experimenting with new practices, and removing systemic blockers, teams become more adaptive and resilient. This mindset fosters learning, reduces waste, and ensures that every feature delivered is part of a smarter, more efficient system—not just another item on a roadmap.

Continuous Improvement:

Builds a Learning Culture

- Encourages curiosity and experimentation.

- Normalizes failure as part of learning.

Improves Delivery Flow

- Identifies and removes systemic blockers.

- Enhances team velocity without burnout.

Empowers Teams

- Teams own their improvement goals.

- Reduces reliance on top-down mandates.

Supports Strategic Adaptability

- Enables fast response to change.

- Aligns operational improvements with strategic outcomes.

## Flow Engineering

“Flow Engineering is a practical guide to using value stream mapping techniques to align teams, unlock innovation, and optimize performance. Its lightweight and iterative practices build the value, clarity, and flow required for effective collaboration and collective action.”

— Steve Pereira & Andrew Davis, Flow Engineering

Flow Engineering reimagines traditional Value Stream Mapping processes by focusing on lightweight, iterative, and visual practices that help teams quickly build shared understanding and take action. It uses five key maps to guide conversations and uncover improvement opportunities:

### Outcome Map

- Clarifies the why behind the work.

- Aligns teams around shared goals and customer value.

### Value Stream Map (Current State)

- Visualizes how work flows today.

- Highlights delays, handoffs, rework, and blockers.

- Focuses on knowledge work, not just manufacturing-style steps.

### Dependency Map

- Surfaces hidden dependencies between teams, systems, or processes.

- Helps reduce coordination overhead and clarify ownership.

### Future State Map

- Defines a target condition for improved flow and value delivery.

- Becomes the basis for experiments and improvement actions.

### Flow Roadmap

The Flow Roadmap is the fifth and final map in Flow Engineering. It organizes the insights, improvement opportunities, and ownership identified in the previous four maps into actionable improvement objectives. After visualizing the current state of their value stream, identifying dependencies, and defining a target condition, teams use the Flow Roadmap to prioritize and plan experiments and changes that will improve delivery flow and customer outcomes.

## Flow Engineering and Kata

The Flow Engineering mapping process provides a structured, visual foundation for executing the Lean Improvement Kata by helping teams understand their current delivery system, define a clear target condition, and identify actionable obstacles. Through tools like the Outcome Map, Current and Future State Value Stream Maps, Dependency Map, and the Flow Roadmap, teams collaboratively surface inefficiencies, clarify ownership, and prioritize improvements. These maps directly support each step of the Kata cycle—diagnosing the current state, setting a target, experimenting toward it, and learning from results—making continuous improvement both accessible and measurable.

## The Flow Roadmap as OKRs

The Flow Roadmap, traditionally used to track improvement actions from Flow Engineering workshops, can be elevated by expressing its items as quarterly team-level OKRs. This approach aligns continuous improvement with strategic planning and reinforces accountability, visibility, and learning.

Each improvement initiative identified through Flow Engineering maps—such as reducing handoffs, improving lead time, or streamlining deployment—can be framed as an objective with clear, quantifiable key results.

Example:

Objective: Improve delivery flow by reducing cross-team handoffs.

Key Results:

- Reduce average handoffs per work item from 4 to 2.

- Increase percentage of work completed within stream-aligned teams from 60% to 85%.

- Achieve a 20% reduction in cycle time for cross-functional items.

This approach ensures that improvement actions are outcome-driven, trackable, and aligned with the team's quarterly cadence. It also enables teams to review and rate their improvement OKRs alongside delivery OKRs during the quarterly review, reinforcing that how teams work is just as important as what they deliver.

## Pattern: Improve Collaboratively

### Context

Teams are under pressure to deliver features quickly, leaving little time for improvement. Retrospectives happen but often result in superficial actions or isolated fixes. Leadership wants better performance but struggles to drive systemic change without micromanaging.

### Problem

Improvement is treated as an afterthought or a leadership mandate. Teams lack ownership, and changes fail to stick because they are imposed rather than co-created. Bottlenecks persist, and learning is slow.

### Forces

- Delivery pressure competes with improvement work.

- Teams fear that raising issues will lead to blame.

- Leaders want measurable progress but lack visibility into systemic blockers.

- Improvement feels disconnected from strategic goals.

### Solution

Embed improvement into the delivery rhythm using Lean Kata and Flow Engineering. Make improvement objectives visible and measurable by expressing them as OKRs. Use collaborative mapping workshops (e.g., Value Stream Maps, Dependency Maps) to surface bottlenecks and design experiments together. Leaders act as coaches, enabling teams to own improvement actions rather than prescribing solutions.

### Result

Improvement becomes continuous, safe, and systemic. Teams experiment with small changes, learn from data, and adapt quickly. Leadership gains visibility through flow metrics and OKRs, guiding with evidence—not control. The organization evolves through collective learning rather than isolated fixes.

### Related Patterns

- Visualize Work

- Flow First

- Coaching Culture

- Time for Reflection

# Continuous Integration (CI) & Continuous Delivery (CD)

“Continuous Integration is a software development practice where members of a team integrate their work frequently, usually each person integrates at least daily—leading to multiple integrations per day. Each integration is verified by an automated build (including test) to detect integration errors as quickly as possible.”

— Martin Fowler, Continuous Integration

“Continuous Delivery is the ability to get changes of all types—including new features, configuration changes, bug fixes, and experiments—into production, or into the hands of users, safely and quickly in a sustainable way.”

— Jez Humble & David Farley, Continuous Delivery: Reliable Software Releases through Build, Test, and Deployment Automation

Continuous Integration (CI) and Continuous Delivery (CD) are foundational to value outcomes-based software delivery because they enable teams to deliver fast, safe, and measurable impact—not just code.

## Continuous Integration (CI)

CI is the practice of frequently committing code changes into a shared repository’s main line or branch (also known as trunk)— at least once per day but often multiple times a day. Each commit triggers automated builds and tests, ensuring that new code integrates smoothly and does not break existing functionality.

Key Practices:

- Trunk-based development

- Automated unit and integration tests

- Build pipelines triggered on commit

- Fast feedback loops

## Continuous Delivery (CD)

CD ensures that every code change is always in a deployable state. It automates the release process so that software can be deployed to production at any time, safely and reliably.

Key Practices:

- Automated deployment pipelines

- Infrastructure as code

- Feature toggles for safe experimentation

- Rollback mechanisms and telemetry

## Problems CI/CD Solves

| Problem | CI/CD Solution |
| --- | --- |
| Integration hell | CI catches issues early through frequent merges and tests |
| Manual, error-prone releases | CD automates deployment and rollback |
| Long feedback loops | CI/CD provides instant feedback on code quality and deployability |
| Risky big-bang releases | CD enables incremental, low-risk deployments |
| Environment drift | Infrastructure as code ensures consistency across environments |

## Why CI/CD Is Crucial for Value Outcomes

1. Faster Feedback Loops

- CI ensures that every code change is tested and integrated quickly.

- CD allows teams to release features as soon as they are ready.

This rapid cycle helps validate whether a change delivers real customer value.

2. Reduced Risk

- Automated testing, rollback mechanisms, and feature toggles make deployments safer.

- Teams can experiment without fear—critical for learning what works.

3. Evidence-Based Delivery

- CI/CD pipelines integrate telemetry and observability.

- Teams can measure impact (e.g. usage, performance, behaviour change) immediately after release.

4. Supports Thin Slices and Iterative Delivery

- Enables small, incremental changes that are easier to validate and refine.

- Aligns perfectly with outcome-driven planning and Lean experimentation.

## How CI/CD Outperforms Legacy Practices

- Speed
Code moves from development to production in hours or days—not weeks or months.

- Quality
Automated testing and telemetry catch issues early and continuously.

- Safety
Feature toggles and rollback mechanisms reduce risk during deployment.

- Adaptability
Teams can respond to change quickly, releasing fixes or features without delay.

- Empowerment
Developers own the full lifecycle of their code, increasing accountability and engagement.

## Pattern: Deliver Continuously

### Context

Your organization struggles with long release cycles, integration issues, and unpredictable deployments. Teams fear breaking production, so releases are infrequent and risky. Feedback loops are slow, making it hard to validate customer impact quickly.

### Problem

Manual builds and deployments create bottlenecks and errors. Integration happens late, leading to “big bang” releases that fail often. Teams spend more time fixing issues than delivering value. Innovation stalls because experimentation feels unsafe.

### Forces

- Stakeholders want speed without sacrificing stability.

- Teams need confidence in their delivery pipeline.

- Manual processes increase risk and slow feedback.

- Pressure to release quickly can compromise quality.

### Solution

Adopt Continuous Integration (CI) and Continuous Delivery (CD) practices to automate and streamline delivery.

- CI: Frequently integrate code into a shared trunk, run automated builds and tests to catch issues early.

- CD: Automate deployments so every change is always in a deployable state. Use feature toggles, rollback mechanisms, and telemetry for safe experimentation.

Embed these practices into EmergentOS to enable iterative delivery, validated learning, and fast feedback loops.

### Result

Delivery becomes fast, safe, and predictable. Teams deploy small changes frequently, reducing risk and improving quality. Feedback loops accelerate learning, enabling outcome-driven decisions. Innovation thrives because experimentation is safe.

### Related Patterns

- Flow First

- Visualize Work

- High Integrity Commitments

- Improve Collaboratively

# The DORA 4 Key Metrics

## What Are the DORA 4 Key Metrics?

The DORA Metrics are four performance indicators identified by the DevOps Research and Assessment (DORA) team, based on years of research into what makes software teams high performing. These metrics are:

### Deployment Frequency

- Measures: How often code is deployed to production

- What ‘good’ looks like: On-demand or multiple times per day (Elite)

- Why it matters: Frequent deployments indicate fast feedback loops and reduced batch sizes.

- Aligned Practices:

  - Trunk-based development

  - CI/CD pipelines

  - Feature toggles and canary releases

### Lead Time for Changes

- Measures: Time from code commit to running in production

- What ‘good’ looks like: Less than one day from code commit to production (Elite)

- Why it matters: Short lead times reflect efficient flow and fast value delivery.

- Aligned Practices:

  - Automated testing and builds

  - Small, incremental changes

  - Stream-aligned teams with clear ownership

### Change Failure Rate

- Measures: Percentage of deployments that cause failures in production

- What ‘good’ looks like: 0–15% of changes cause failures (Elite/High)

- Why it matters: Low failure rates indicate quality and reliability in delivery.

- Aligned Practices:

  - Automated regression testing

  - Observability and telemetry

  - Safe deployment strategies (e.g. blue/green, rollback)

### Mean Time to Recovery (MTTR)

- Measures: Time it takes to restore service after a failure

- What ‘good’ looks like: Less than one hour to restore service (Elite)

- Why it matters: Fast recovery minimizes customer impact and builds resilience.

- Aligned Practices:

  - Real-time monitoring and alerting

  - Runbooks and incident response playbooks

  - Blameless postmortems and continuous learning

Together, these metrics provide a balanced view of speed and stability. High-performing teams do not just ship fast—they ship safely, learn quickly, and recover gracefully. Tracking these metrics helps teams identify bottlenecks, validate engineering practices, and guide continuous improvement.

## How The Metrics Arose

The DORA metrics emerged from a multi-year research program led by Nicole Forsgren, Jez Humble, and Gene Kim, culminating in the book Accelerate. The team analysed data from thousands of organizations across industries and found that these four metrics consistently correlated with better business outcomes, including:

- Higher profitability and increased market share

- Faster time-to-market

- Better customer satisfaction

- Lower burnout and team stress

Their findings were backed by statistical analysis and longitudinal studies, making DORA metrics one of the most evidence-based frameworks in software delivery.

## Why DORA Metrics Drive Successful Delivery

Empirical Insight

- Replaces anecdotal performance reviews with quantifiable data.

- Enables teams to track progress and identify bottlenecks.

Balanced View of Speed and Stability

- Encourages fast delivery without sacrificing quality.

- Helps teams avoid the “move fast and break things” trap.

Supports Continuous Improvement

- Metrics are reviewed regularly to guide Lean Kata experiments.

- Trends inform coaching and investment decisions.

Team-Level Ownership

- Metrics are visible and actionable at the team level.

- Empowers teams to improve autonomously.

## Strategic Impact in EmergentOS

In this outcome-driven operating system:

- DORA metrics are reviewed monthly to correlate engineering practices with business outcomes.

- Leaders use trends—not targets—to coach teams.

- Combined with Kanban flow metrics, they provide a full picture of delivery health.

## Pattern: Measure What Matters

### Context

Your organization wants to improve delivery performance but relies on anecdotal feedback or vanity metrics like “number of features shipped.” Teams lack objective data to guide improvement, and leadership struggles to identify bottlenecks or validate progress.

### Problem

Without meaningful metrics, improvement efforts are blind. Decisions are based on assumptions, not evidence. Teams optimize for output rather than flow or stability, leading to burnout and poor customer experience.

### Forces

- Stakeholders want proof of progress and ROI.

- Teams need actionable insights, not arbitrary targets.

- Traditional metrics (e.g., velocity, story points) do not correlate with business outcomes.

- Fear of measurement being used punitively undermines trust.

### Solution

Adopt the DORA 4 Key Metrics—Deployment Frequency, Lead Time for Changes, Change Failure Rate, and Mean Time to Recovery—as the foundation for empirical governance. These metrics provide a balanced view of speed and stability. Use them to:

- Track engineering health and delivery flow.

- Guide coaching and improvement experiments.

- Correlate technical practices (e.g., CI/CD, trunk-based development) with business outcomes. Review trends regularly, focusing on learning and improvement—not punishment.

### Result

Teams gain clarity on what drives performance. Leadership makes evidence-based decisions. Delivery becomes faster and safer, with resilience built into the system. Improvement efforts are targeted and measurable, fostering trust and transparency.

### Related Patterns

- Deliver Continuously

- Flow First

- Improve Collaboratively

- Visualize Work

# Mik Kersten’s Flow Framework

Mik Kersten’s Flow Framework is a powerful model for aligning software delivery with business outcomes. It was introduced in his book Project to Product and is designed to help organizations manage software delivery as a value stream, bridging the gap between business strategy and technical execution.

## What Is the Flow Framework?

The Flow Framework provides a structured approach to Value Stream Management (VSM). It enables organizations to measure, visualize, and optimize the flow of work across product value streams. Its goal is to shift focus from project-based delivery to product-centric value creation.

Key principles include:

- Product-centric thinking: Organize around long-lived product value streams, not temporary projects.

- Flow Metrics: Quantify how work moves through the value stream.

- Business-technology alignment: Use shared metrics to connect technical teams with business stakeholders.

## The Four Flow Items

Flow Items represent the types of work that flow through a software value stream. They are mutually exclusive and collectively exhaustive (MECE), meaning every unit of work should fit into one—and only one—category:

| Flow Item | Description |
| --- | --- |
| Feature | New business value delivered to customers (e.g., new functionality) |
| Defect | Work to fix problems that degrade user experience or system performance |
| Risk | Work to address security, compliance, or architectural risks |
| Debt | Work to improve maintainability, scalability, or reduce technical debt |

These categories help teams and leaders understand where effort is going and how it aligns with strategic goals.

### Flow Items and Their Mapping to EmergentOS

Flow Items represent the categories of work that move through a software value stream in Mik Kersten’s Flow Framework. They provide clarity on where effort is invested and how it aligns with strategic priorities. The four Flow Items are:

- Feature: New business value delivered to customers.

Mapping in EmergentOS: Features align with OKRs and customer outcomes. They are visualized in team and portfolio Kanban boards and tracked against delivery OKRs.

- Defect: Work to fix quality issues or bugs.

Mapping in EmergentOS: Defects appear in Kanban boards and influence engineering OKRs. DORA metrics (e.g., Change Failure Rate, MTTR) validate improvements in defect handling.

- Risk: Work to reduce security, compliance, or operational risks.

Mapping in EmergentOS: Risks are prioritized during quarterly planning and visualized in portfolio Kanban. Flow Distribution helps ensure risk work is not neglected.

- Debt: Work to reduce technical debt and improve maintainability.
Mapping in EmergentOS: Debt reduction is embedded in Slowification windows and Lean Kata cycles. Improvement OKRs often target debt reduction to sustain flow and adaptability.

By mapping Flow Items to EmergentOS practices, organizations gain visibility into trade-offs between innovation, quality, risk mitigation, and sustainability. This supports evidence-based prioritization and holistic governance.

## What Is Flow Distribution?

Flow Distribution refers to the proportion of each Flow Item type within a value stream over a given period. It reveals how a team’s capacity is being allocated across competing priorities.

### Why It Matters:

- Strategic alignment: Ensures the team’s work reflects business priorities (e.g., innovation vs. risk mitigation).

- Trade-off visibility: Highlights when focusing on one area (e.g., features) delays others (e.g., defects).

- Continuous improvement: Enables data-driven conversations about resource allocation and bottlenecks.

For example, if 80% of work is features and only 5% is debt, it might signal a future slowdown due to accumulating technical debt.

## The Five Flow Metrics

Each metric captures a different dimension of how work moves through a value stream:

| Metric | Description | What It Reveals |
| --- | --- | --- |
| Flow Velocity | Number of Flow Items completed over time | Delivery throughput and productivity |
| Flow Time | Total time from start to finish for a Flow Item | Speed of delivery and time-to-value |
| Flow Efficiency | Ratio of active work time to total Flow Time | Waste and delays in the process |
| Flow Load | Number of Flow Items currently in progress | Capacity and potential overload |
| Flow Distribution | Proportion of work across Flow Item types (Feature, Defect, Risk, Debt) | Strategic alignment and trade-offs |

These metrics are designed to be agnostic to Agile and DevOps tooling, making them applicable across diverse delivery environments.

Flow Metrics are not just operational indicators—they act as strategic levers for business impact. By measuring Flow Velocity and Flow Time, organizations can correlate delivery speed and throughput with customer-facing OKRs, ensuring faster time-to-value. Flow Distribution provides visibility into how capacity is allocated across innovation (features), risk mitigation, and technical debt reduction, enabling evidence-based prioritization and investment decisions. When combined with DORA metrics, Flow Metrics create a dual governance lens: engineering health and value stream performance. This empowers leaders to align delivery with strategic outcomes, optimize resource allocation, and continuously improve both technical and business dimensions.

### Flow States

Flow States describe the stages a Flow Item (Feature, Defect, Risk, Debt) passes through in a value stream. They help visualize and measure how work progresses from idea to delivery.

The Flow Framework defines Flow States to measure how work progresses through the value stream. These states are:

| State | Definition | How it’s used |
| --- | --- | --- |
| New | The Flow Item has been created but work has not started | Represents demand entering the value stream |
| Active | The Flow Item is being worked on (design, development, testing) | Used to calculate Flow Efficiency (active vs wait time) |
| Waiting | The Flow Item is blocked or paused (e.g., waiting for approval, dependency resolution) | Critical for identifying bottlenecks and waste |
| Done | The Flow Item is completed and delivered to the customer or deployed | Used to calculate Flow Time and Flow Velocity |

## Measuring Value Delivery with the Flow Framework

The Flow Framework measures value delivery by:

- Tracking Flow Items (Feature, Defect, Risk, Debt) through the entire value stream

- Quantifying delivery performance using Flow Metrics

- Aligning work with business outcomes by visualizing trade-offs and bottlenecks

Key Benefits:

- Business-technology alignment: Metrics translate technical activity into business-relevant insights

- Investment visibility: Leaders can see where time and resources are going

- Continuous improvement: Teams can identify constraints and optimize flow

For example, if Flow Time for Features is increasing while Flow Load is high, it may indicate overcommitment or bottlenecks. If Flow Distribution shows a spike in Defects, it may signal quality issues that need attention.

## The EmergentOS – Flow Framework Synergy

EmergentOS and Mik Kersten’s Flow Framework share a common goal: optimizing the flow of value across technology delivery. Integrating Flow Framework into EmergentOS strengthens empirical governance and connects delivery performance to business outcomes.

- Both frameworks emphasize value stream thinking and flow-based delivery.

- EmergentOS provides the operating rhythm and cultural scaffolding; Flow Framework adds a robust measurement layer.

- Together, they create a closed-loop system:

### How Flow Metrics and DORA Metrics Work Together

- Flow Metrics provide visibility into systemic delivery health and bottlenecks.

- DORA metrics measure engineering performance and stability.

- Combined, they offer a holistic view of speed, quality, and adaptability—enabling leaders to coach through evidence, not assumptions.

#### Integration Points

- Embed Flow Metrics and DORA metrics into EmergentOS governance rituals (monthly reviews, quarterly retrospectives).

- Use Flow Metrics to guide improvement OKRs and Flow Roadmaps.

- Use DORA trends to validate engineering practices and correlate with business outcomes.

This integration replaces anecdotal performance reviews with empirical data, enabling organizations to optimize for both flow and stability while aligning delivery with strategic outcomes.

### Flow Metrics vs Kanban Metrics: Complementary Insights

Flow Framework’s Flow Metrics and Kanban’s flow metrics share common goals—visualizing and improving delivery flow—but operate at different scopes. Kanban metrics focus on team-level predictability, while Flow Metrics provide strategic insight into value stream health. EmergentOS leverages both for a holistic view of performance.

| Metric Type | Kanban Metrics | Flow Framework Metrics |
| --- | --- | --- |
| Speed | Throughput | Flow Velocity |
| Predictability | Cycle Time, Lead Time | Flow Time |
| Efficiency | Flow Efficiency | Flow Efficiency |
| Workload | Work-In-Progress (WIP) | Flow Load |
| Strategic Balance | N/A | Flow Distribution |

How EmergentOS Uses Both:

- Kanban metrics guide daily team decisions and improvement experiments.

- Flow Metrics inform portfolio-level governance, coaching, and strategic alignment.

Together, they provide actionable insights at both operational and strategic levels.

# What EmergentOS Looks Like in Action

## Week 1–2: Strategy & Alignment

1. Strategic Outcome Mapping

Product leadership facilitates Strategic Outcome Mapping sessions to define problems worth solving and clarify strategic intent. These sessions identify target outcomes, customer behaviours to influence, and experiments needed to validate assumptions.

2. Build or Refresh Lean Value Trees (LVTs)

Translate strategic themes into bets, value streams, and initiatives. LVTs provide the strategic map that connects company-level goals to actionable work.

3. Align OKRs to LVT Branches

Ensure every key result ties back to a strategic hypothesis. OKRs cascade from LVT branches for consistency and alignment.

4. Feed Prioritized Initiatives into Portfolio Kanban

Move initiatives into Portfolio Kanban stages (Funnel → Review → Analysis → Ready for Planning) to enable flow-based governance and capacity planning.

5. Visualize Dependencies and Team Interactions

Use Team Topology maps to surface dependencies and clarify interaction modes, reducing cognitive load and coordination overhead.

6. Plan Experiments and Hypotheses

Teams identify hypotheses and design experiments (e.g., spikes, prototypes, A/B tests, Google Sprints) to validate assumptions early and reduce uncertainty before commitments.

7. Run Mapping Workshops and Create Flow Roadmap

Conduct Value Stream Mapping and Dependency Mapping workshops to define the current state and target condition for improvement. Capture improvement actions, owners, and expected outcomes in the Flow Roadmap.

## Week 3–11: Discovery & Delivery

1. Visualize and Manage Work

Teams deliver iteratively, visualizing work in Kanban boards with clear tags for discovery, delivery, and improvement. Portfolio Kanban tracks initiative flow across the organization, applying WIP limits and surfacing systemic blockers.

2. Validate Hypotheses Through Experiments

Spikes, prototypes, and A/B tests reduce uncertainty and inform technical decisions. These experiments validate assumptions before scaling delivery.

3. Deliver in Thin Slices

Teams build thin slices of functionality to test value quickly and iteratively, enabling fast feedback and reducing risk.

4. Monitor Flow and Engineering Health

Weekly reviews of flow metrics, DORA indicators, and Portfolio Kanban health guide operational decisions. Leaders coach through evidence, not timelines.

5. Execute Improvement Actions

Teams run Lean Kata experiments and Flow Roadmap items alongside delivery work. Progress is tracked using flow metrics and retrospectives, embedding continuous improvement into the delivery rhythm.

## Week 12: Validation & Retrospective

1. Validate Outcomes Against Hypotheses

Use telemetry, customer feedback, and experiment results to confirm or adjust hypotheses defined in LVTs.

2. Review OKRs and Strategic Alignment

Assess delivery and improvement OKRs, scoring progress and identifying gaps. Ensure alignment with LVT branches and strategic themes.

3. Portfolio Kanban Review

Evaluate initiative flow, systemic blockers, and WIP health. Identify items to retire, pivot, or carry forward.

4. Update Lean Value Trees

Refresh LVTs based on validated learning—confirm bets, adjust priorities, and add new hypotheses for the next cycle.

5. Retrospectives and Flow Roadmap Refresh

Run retrospectives focused on delivery performance and learning effectiveness. Update the Flow Roadmap with new improvement actions for the next quarter.

6. Strategy Refresh

Use insights from validation and retrospectives to inform company-level strategy and portfolio priorities for the upcoming quarter.

Note: The output of the Week 1 Strategy & Alignment (“Slowification”) period is not a traditional plan, a Gantt chart, or a feature roadmap. Instead, it is a concise set of Objectives and Key Results (OKRs) for problems to solve that are: - Strategically aligned with business objectives - Focused on measurable outcomes, not outputs - Designed to deliver quantifiable value and drive continuous improvement in both product and ways of working These OKRs provide clarity of purpose without prescribing solutions, enabling teams to adapt as they learn. Where deadlines are essential, teams make High Integrity Commitments—based on validated discovery, practice, and learning—rather than speculative estimates. This ensures commitments are grounded in evidence and confidence, not guesswork.

At the portfolio level, leaders track progress through Portfolio Kanban boards, flow metrics, and DORA trends, ensuring visibility into both strategic bets and delivery health. Instead of managing timelines and estimates, they coach teams toward better flow, validated outcomes, and faster learning. Lean Value Trees provide the strategic map, while Portfolio Kanban acts as the execution engine—enabling leaders to make evidence-based decisions and adapt priorities as new insights emerge.

By embedding these techniques, EmergentOS becomes not just adaptive—but intelligently adaptive. It empowers teams to make better decisions, faster, and with evidence.

# Strategic Impact

EmergentOS does not just improve delivery—it transforms how organizations think, plan, and learn. It fosters:

Modularity & Composability

Each element (OKRs, Kanban, Lean Value Trees, Portfolio Kanban, Kata, CI/CD) can be introduced independently and scaled as maturity grows.

Empirical Thinking

Decisions are driven by telemetry, flow metrics, and validated learning—not estimates or gut feel. Lean Value Trees reinforce this by grounding initiatives in hypotheses and measurable outcomes.

Quarterly Rhythm

Aligns strategy and delivery without the overhead of PI planning or release trains. LVTs and OKRs refresh quarterly, ensuring adaptability and strategic clarity.

Team-Centricity

Shifts the locus of control to the team level, enabling faster decisions and deeper ownership. Teams own hypotheses and outcomes, not just tasks.

Strategy-to-Execution Loop

Lean Value Trees provide the strategic map, OKRs define measurable goals, and Portfolio Kanban operationalizes flow. This creates a closed loop:

Strategic Themes → LVTs → OKRs → Portfolio Kanban → Delivery → Feedback → Strategy Refresh.

EmergentOS is designed for scale but built for speed. It empowers teams without losing sight of strategy. And it replaces control with clarity—so leaders can guide, not govern.

# Delivery, Delivery, Delivery Vs Keeping the Lights On

There is an intrinsic and often underappreciated tension between product delivery—the push to build new features and ship value—and the need to “keep the lights on” (KTLO) through operational maintenance, technical debt management, and system reliability. This tension is especially pronounced in fast-moving organizations where speed is prized, but sustainability is essential.

## Understanding the Tension

Product Delivery

- Focuses on building new capabilities, meeting customer needs, and driving growth.

- Often measured by velocity, roadmap progress, and feature output.

- Driven by strategic goals, market demands, and stakeholder expectations.

Keeping the Lights On

- Involves maintaining system stability, resolving incidents, and supporting existing functionality.

- Includes managing technical debt, refactoring, and infrastructure upkeep.

- Often invisible until something breaks—but critical for long-term health.

The tension arises because delivery work is visible and celebrated, while maintenance work is often hidden and deprioritized. Yet neglecting technical health leads to slower delivery, more bugs, and burnout.

## Strategies for Balancing Product Delivery and KTLO

1. Use OKRs to Balance Strategic and Technical Goals

- Include technical health objectives alongside customer-facing ones.

- Example:

  - Objective: Improve platform stability

  - Key Results: Reduce incident frequency by 30%, refactor legacy module X

2. Visualize All Work in Kanban

- Make operational and technical debt work visible on boards.

- Use swim lanes or tags to distinguish between delivery, maintenance, and improvement.

3. Apply Lean Kata to Technical Debt

- Treat debt reduction as a target condition.

- Run experiments to improve flow, reduce complexity, or increase test coverage.

4. Track Flow Metrics and DORA Indicators

- Use metrics like cycle time, change failure rate, and MTTR to surface hidden costs of poor technical health.

- Use trends to guide coaching and investment—not just delivery pressure.

5. Embed Slowification Windows

- Dedicate time in the quarterly cadence (e.g. Weeks 1–2 or 12) for refactoring, learning, and system improvement.

- Normalize the idea that slowing down strategically enables faster, safer delivery.

6. Empower Teams to Own Reliability

- Stream-aligned teams should own not just features, but the operational health of their domain.

- Encourage a culture of engineering excellence, not just feature throughput.

# Governance: Purpose and Function

Within EmergentOS, governance plays a supportive and enabling role, rather than a controlling or prescriptive one. It is intentionally lightweight, decentralized, and focused on clarity, transparency, and continuous learning.

## Enablement Over Control

Governance is designed to guide teams, not govern them. It provides strategic clarity through tools like OKRs,  Strategic Outcome Mapping, and Portfolio Kanban, while allowing teams autonomy in how they deliver.

## Evidence-Based Oversight

Instead of relying on estimates, timelines, or feature counts, governance is driven by empirical data:

- DORA metrics for engineering performance

- Flow metrics for value stream and delivery health

- Telemetry and user feedback for outcome validation

This ensures decisions are based on real performance, not assumptions.

## Quarterly Rhythm and Review

Governance is embedded in the quarterly cycle, where:

- OKRs are reviewed and rated

- Flow Roadmaps are assessed and refreshed

- Strategy is updated based on validated learning

This rhythm replaces traditional release trains or PI planning with adaptive, outcome-driven planning.

## Coaching and Maturity Support

Governance also includes coaching rituals and maturity tracks to help teams evolve. It supports:

- Team topology tune-ups

- Lean Kata retrospectives

- OKR planning and alignment workshops

This ensures governance is developmental, not punitive.

## Strategic Impact of Governance

- Transparency: Everyone sees what matters and how success is measured.

- Alignment: Teams stay connected to business strategy without micromanagement.

- Trust: Leaders guide through coaching and data—not control.

- Scalability: Governance scales through modular practices and team autonomy.

## Intent Based Leadership

Intent-Based Leadership (IBL), as introduced by David Marquet, is a leadership philosophy that shifts decision-making authority to those closest to the work, fostering ownership, competence, and clarity. It is built on the idea of leaders creating leaders—not followers—by giving control, increasing competence, and ensuring clarity of purpose.

### How Intent Based Leadership Works

#### Scenario: Empowering a Stream-Aligned Product Team

##### Context:

A product team is responsible for improving the onboarding experience for new users. The team has identified a potential solution: redesigning the onboarding flow to reduce time-to-value.

##### Traditional Leadership Approach:

- The manager reviews the plan and gives instructions:
“Redesign the onboarding flow to reduce time-to-value by 50%. Complete it by the end of the quarter.”

- The team executes the task but feels little ownership. Decisions are escalated. Innovation is limited.

##### Intent-Based Leadership Approach:

- The team lead or manager uses IBL principles:
“I intend to give the team full control over the onboarding redesign. You have the context, the data, and the skills. Let me know what support you need.”

- The team responds:
“We intend to run a spike and prototype two onboarding flows. We will use telemetry to validate which one reduces time-to-value most effectively. We will commit to the best option by week 4.”

- The manager:

  - Ensures clarity of purpose (OKRs: reduce onboarding time).

  - Builds competence (supports access to user data, design tools).

  - Gives control (lets the team decide how to solve the problem).

##### Result

- The team feels trusted and motivated.

- They innovate faster and validate their solution with real data.

- The onboarding flow is redesigned based on evidence—not assumptions.

- The team delivers a measurable outcome: onboarding time reduced by 50%.

### How Intent Based Leadership Fits into EmergentOS

Intent Based Leadership is deeply embedded in the operating system’s principles and practices; EmergentOS decentralizes control, fosters clarity, builds competence, and empowers teams:

| IBL Principle | EmergentOS Alignment | Practical Outcome |
| --- | --- | --- |
| Give Control | Team-Centric Autonomy | Team owns the solution and delivery |
| Increase Competence | Coaching Playbooks, Lean Kata | Team runs experiments and learns |
| Ensure Clarity | OKRs, Outcome Mapping | Team understands the strategic goal |
| Create Leaders | Coaching-Led Governance | Team members lead discovery and delivery |

#### Principles and Alignment

1. Empowered Teams & Decentralized Decision-Making

- EmergentOS Principle: Team-Centric Autonomy — stream-aligned teams own outcomes and make decisions.

- IBL Alignment: IBL encourages pushing decision-making to the edge, trusting teams to act with intent.

Fit: Direct. EmergentOS’s emphasis on autonomy and ownership mirrors IBL’s core philosophy.

2. Clarity of Purpose via OKRs

- EmergentOS Practice: OKRs provide strategic alignment and outcome focus.

- IBL Alignment: Leaders ensure clarity so teams can make informed decisions.

Fit: Strong. OKRs serve as the “why” behind the work, enabling intent-based action.

3. Coaching-Led Governance

- EmergentOS Practice: Managers act as coaches, not controllers.

- IBL Alignment: Leaders shift from giving orders to enabling others to lead.

Fit: Perfect. The coaching playbook and rituals support IBL’s leadership transformation.

4. Continuous Learning & Improvement

- EmergentOS Practice: Lean Kata, Flow Engineering, and telemetry-driven retrospectives.

- IBL Alignment: Competence is built through learning and experimentation.

Fit: Strong. EmergentOS embeds learning into delivery, supporting IBL’s emphasis on growing capability.

5. Trust and Psychological Safety

- EmergentOS Value Alignment: Trust and Kindness are core values.

- IBL Alignment: Trust is foundational - leaders must trust teams to act with intent.

Fit: Deep. EmergentOS’s cultural emphasis reinforces IBL principles.

## Pattern: Coaching Culture

### Context

Your organization aspires to become more adaptive and outcome-driven but still relies on traditional management practices. Leaders often focus on tasks, deadlines, and reporting, which limits team autonomy and learning. Teams need guidance and support to grow, improve, and feel safe to experiment.

### Problem

Without a coaching mindset, leaders inadvertently stifle innovation and adaptability. Teams become compliance-driven, not outcome-driven. Continuous improvement feels optional instead of embedded.

### Forces

- Leaders feel pressure to provide predictability and maintain confidence across the organization.

- Teams seek guidance and clarity but want to avoid micromanagement.

- Existing cultural norms often emphasize authority and control over empowerment and autonomy.

- Coaching capabilities are not yet widespread and require intentional development and support.

### Solution

Shift leadership from directing to coaching. Equip managers with playbooks and rituals that foster clarity, competence, and autonomy. Embed coaching into governance through OKR reviews, flow metrics discussions, and retrospectives. Leaders ask enabling questions like:

- “What’s blocking flow?”

- “Where do you need time to learn or improve?”

- “How can I help remove obstacles?”

Use Intent-Based Leadership principles: give control, increase competence, and ensure clarity. Make coaching a visible, measurable part of leadership responsibilities.

### Result

Teams feel trusted and supported. Leaders guide through data and dialogue, not directives. Continuous improvement becomes systemic. Psychological safety grows, enabling experimentation and learning. The organization evolves faster and more sustainably.

### Related Patterns

- Time for Reflection

- Outcome Over Output

- Improve Collaboratively

- Big Picture

# How To Adopt EmergentOS: Just Do It!

“Think big, start small, learn fast. Start with a compelling vision, break it down into small experiments, and iterate quickly to maximize learning and minimize risk.”
— Jonathan Smart, Sooner Safer Happier

EmergentOS is designed for simplicity in adoption. Unlike prescriptive frameworks that require big-bang transformations, EmergentOS thrives on incremental change and validated learning. Its modular, composable architecture means you can start with a single practice—such as visualizing work with Kanban or defining outcome-based OKRs—and expand gradually as maturity grows.

Why this works:

- Modular Architecture: Practices like Lean Value Trees, OKRs, Portfolio Kanban, CI/CD, and Lean Kata can be introduced independently.

- Evolutionary Change: Start with what you do now and layer in additional practices over time, reducing risk and resistance.

- Immediate Value: Even small steps, like making work visible or defining measurable outcomes, deliver quick wins and build momentum.

- Empirical Governance: EmergentOS does not require upfront certainty—it learns by doing, making incremental adoption natural.

- No Heavyweight Prerequisites: No new roles, ceremonies, or organizational upheaval are needed before starting.

Core Idea:

EmergentOS is adaptive by design. Its strength lies in enabling organizations to learn by doing, making adoption frictionless, scalable, and sustainable.

## The Positive Feedback Loop

EmergentOS creates a self-sustaining positive feedback loop that amplifies adaptability and performance over time. This loop works because every improvement feeds back into strategy and planning:

- Start Small → Immediate Wins

Adopting even one practice—such as Kanban or OKRs—creates visibility and clarity, improving decision-making and flow.

- Visibility → Learning → Adaptation

Kanban boards, flow metrics, and telemetry make progress and bottlenecks visible. Teams learn from real data, not assumptions, and adapt quickly.

- Learning → Confidence → Expansion

Validated learning builds confidence. Teams feel safe to experiment and adopt additional practices like Lean Value Trees or Portfolio Kanban.

- Expansion → Greater Alignment & Flow

As more practices integrate (OKRs + LVTs + Kanban), strategy and execution align better, improving flow and outcomes.

- Improved Outcomes → Reinforced Trust

Delivering measurable impact strengthens trust between teams and leadership, reinforcing autonomy and continuous improvement.

Result:

Each cycle of visibility → learning → adaptation → improvement makes the system stronger. EmergentOS is designed to amplify this loop, creating a culture of continuous learning and strategic adaptability.

# Maturity Model

## Maturity Levels

Strategic Alignment

- Level 1: No clear strategy or goals; teams work in isolation

- Level 2: Basic goals exist but lack measurable outcomes or alignment

- Level 3: Company-level OKRs exist; some teams align loosely

- Level 4: Portfolio-level outcome mapping and initial Lean Value Trees; teams align OKRs to strategy

- Level 5: Fully cascaded OKRs and mature Lean Value Trees; strategy drives team-level outcomes and prioritization; Portfolio Kanban operationalizes flow

Team Autonomy

- Level 1: Teams are task-driven with little decision-making power

- Level 2: Some autonomy in delivery; decisions still centralized

- Level 3: Stream-aligned teams with partial ownership of outcomes

- Level 4: Teams own delivery and improvement; empowered by leadership

- Level 5: Teams fully own outcomes, flow, and improvement; operate with high trust and hypothesis-driven planning

Flow Management

- Level 1: Work is managed via ad hoc tasks or Gantt charts

- Level 2: Basic Kanban boards used; limited flow metrics

- Level 3: Kanban with WIP limits and aging metrics; some visibility

- Level 4: Flow metrics used for coaching and improvement

- Level 5: Portfolio-level Kanban integrated with LVTs; flow guides prioritization and strategy

Engineering Practices

- Level 1: Manual builds and deployments; low automation

- Level 2: Basic CI pipelines; some automated testing

- Level 3: CI/CD pipelines with trunk-based development

- Level 4: Feature toggles, telemetry, and rollback strategies

- Level 5: Elite DORA metrics performance; engineering enables fast, safe delivery

Continuous Improvement

- Level 1: Retrospectives are infrequent or superficial

- Level 2: Teams run basic retros; improvement is reactive

- Level 3: Lean Kata cycles used for targeted improvement

- Level 4: Flow Engineering maps guide systemic improvement 
Level 5: Improvement OKRs tracked quarterly; learning drives strategy and updates LVTs

Governance

- Level 1: Governance is top-down and control-oriented

- Level 2: Governance includes planning ceremonies and reporting

- Level 3: Governance supports team autonomy with light oversight

- Level 4: Governance uses metrics and coaching to guide teams

- Level 5: Governance is developmental; strategy adapts based on validated learning and Portfolio Kanban insights

Leadership

- Level 1: Leaders make decisions and give orders. Teams execute tasks with little

- autonomy

- Level 2: Leaders manage work through goals and KPIs. Some delegation, but decisions remain centralized

- Level 3: Leaders begin to coach and support teams. Decision-making starts to decentralize

- Level 4: Leaders give control, build competence, and ensure clarity. Teams express intent and lead execution

- Level 5: Leadership is distributed. Everyone is a leader within their domain. Strategy adapts through collective learning and hypothesis-driven planning

# Coaching Playbook

## Quarterly Coaching Cadence

| Week | Focus | Coaching Activities |
| --- | --- | --- |
| Week 1 | Strategy & Alignment | Strategic Outcome Mapping, Build/Refresh Lean Value Trees, Align OKRs, Portfolio Kanban Setup |
| Week 2–3 | Flow & Empowerment | Value Stream Mapping, Team Topology Tune-Up, Kanban Calibration, Dependency Visualization |
| Week 4–8 | Delivery & Learning | CI/CD Coaching, Experiment Design for Hypothesis Validation, DORA Metrics Setup, Flow Metrics Review |
| Week 9 | Retros & Improvement | Lean Kata Retrospectives, Flow Roadmap Progress Review, Coaching Feedback |
| Week 10–12 | Planning Next Cycle | OKR Review, Outcome Validation, Update Lean Value Trees, Strategy Refresh |

## Team Maturity Coaching Tracks

### Foundational Teams

Goal: Shift from output to outcome, visualize work, and reduce cognitive load.

Coaching Tools:

- Outcome vs Output Workshops

- Kanban Setup & Flow Mapping

- Lean Kata Starter Kit

Artifacts:

- Team Kanban board

- Weekly blocker review

- Simple OKR draft

### Emerging Teams

Goal: Empower product leadership, optimize flow, and introduce CI/CD.

Coaching Tools:

- OKR Planning Facilitation

- Value Stream Mapping

- CI/CD Pipeline Walkthrough

- Intro to Lean Value Trees (LVTs)

Artifacts:

- Quarterly OKRs

- Flow metrics

- DORA baseline metrics

- Initial LVT branch for team initiatives

### Advanced Teams

Goal: Strategic alignment, cross-team flow, outcome validation.

Coaching Tools:

- Team Topology Tune-Ups

- Experiment Mapping for Hypothesis Validation

- DORA Deep Dives

- Portfolio Kanban Coaching

Artifacts:

- Portfolio Kanban board

- Experiment log

- Outcome telemetry dashboard

- Updated Lean Value Tree branches linked to OKRs

### Coaching Tools & Templates

| Tool | Purpose | Format |
| --- | --- | --- |
| Outcome Mapping Canvas | Link strategic themes to customer outcomes and hypotheses | Figma / Miro / Whiteboard |
| Lean Value Tree Template | Visualize strategic themes, bets, value streams, and initiatives | Diagram / Digital Canvas |
| Portfolio Kanban Board | Track initiative flow and dependencies across the portfolio | Jira / Kanban Tool |
| Lean Kata Tracker | Track improvement experiments and target conditions | Spreadsheet / Dashboard |
| Team Topology Map | Visualize team interactions and dependencies | Diagram |
| OKR Planning Guide | Facilitate quarterly alignment and cascade goals | Template |
| Flow Metrics Dashboard | Monitor delivery health and systemic flow | Power BI / Grafana |
| DORA Metrics Tracker | Measure engineering performance and stability | CI/CD Tool Integration |
| Telemetry Dashboard | Validate outcomes and customer impact | Analytics Platform |

### Coaching Rituals

- Weekly Flow Review:

Team Kanban + Portfolio Kanban review, blocker analysis, and flow metrics discussion.

- Monthly Kata Retros:

Reflect on improvement experiments, validate hypotheses, and review Flow Roadmap progress.

- Quarterly OKR & LVT Planning:

Align outcomes, refresh Lean Value Trees, and cascade OKRs.

- Quarterly Outcome Review:

Validate impact using telemetry, customer feedback, and experiment results.

- Portfolio Kanban Sync:

Assess initiative flow, systemic blockers, and WIP health for coaching-led governance.

- Topology Tune-Ups:

Adjust team interactions and dependencies to optimize flow and reduce cognitive load.

### Coaching Success Metrics

| Metric | Description |
| --- | --- |
| % of teams with visible OKRs | Alignment adoption across teams |
| % of initiatives linked to LVTs | Strategic clarity and hypothesis-driven planning |
| Flow efficiency improvement | Delivery health and systemic flow optimization |
| Portfolio Kanban WIP health | Governance through flow-based prioritization |
| DORA metric trends | Engineering performance and stability |
| Number of experiments run | Strength of learning culture and hypothesis testing |
| Telemetry coverage for outcomes | Evidence-based validation of customer impact |
| Reduction in cross-team blockers | Dependency management and collaboration health |

# Key Competencies for Successful Implementation

## Strategic Alignment & Outcome Thinking

Competency: Ability to define and cascade customer-centric goals using OKRs and Lean Value Trees (LVTs).

Why it matters: Shifts focus from feature delivery to measurable impact and strategic clarity.

Skills needed:

- OKR facilitation

- Outcome mapping

- Lean Value Tree creation and prioritization

- Strategic planning

## Team Design & Interaction Management

Competency: Structuring teams using Team Topologies to optimize flow and reduce dependencies.
Why it matters: Enables scalable autonomy and reduces coordination overhead.
Skills needed:

- Team topology mapping

- Interaction mode facilitation

- Cognitive load assessment

## Flow Visualization & Delivery Management

Competency: Using Kanban and Portfolio Kanban to manage work-in-progress and highlight blockers.
Why it matters: Improves transparency, prioritization, and delivery predictability.
Skills needed:

- Kanban board setup and calibration

- Portfolio Kanban configuration

- Flow efficiency analysis

## Continuous Improvement Culture

Competency: Running Lean Kata cycles and Value Stream Mapping to drive operational excellence.
Why it matters: Embeds learning and experimentation into the delivery rhythm.
Skills needed:

- Kata coaching

- Value Stream Mapping facilitation

- Experiment design and tracking

## Engineering Excellence

Competency: Implementing CI/CD pipelines, trunk-based development, and infrastructure as code.

Why it matters: Enables fast, safe, and reliable delivery.

Skills needed:

- DevOps practices

- Test automation

- Feature toggle and rollback strategies

## Empirical Performance Measurement

Competency: Tracking and interpreting DORA metrics and Flow Metrics to guide coaching and improvement.
Why it matters: Replaces anecdotal reviews with data-driven insights.
Skills needed:

- DORA metric setup and analysis

- Flow Metrics interpretation

- Telemetry integration

- Coaching based on trends

## Hypothesis-Driven Planning

Competency: Formulating and validating hypotheses for initiatives using LVTs and telemetry.
Why it matters: Ensures adaptability and reduces waste through evidence-based decisions.
Skills needed:

- Hypothesis framing

- Experiment design

- Outcome validation

## Coaching & Change Enablement

Competency: Supporting teams through maturity tracks and coaching rituals.
Why it matters: Ensures sustainable adoption and cultural transformation.
Skills needed:

- Agile and lean coaching

- Facilitation of retrospectives and planning

- Change management and stakeholder engagement

# Summary

EmergentOS is more than an operating model—it is a strategic system for adaptability and value delivery. It transforms how organizations think, plan, and execute, creating a closed loop between strategy and delivery.

It fosters:

Modular & Composable Adoption

Each practice—Lean Value Trees (LVTs), OKRs, Portfolio Kanban, Lean Kata, CI/CD—can be introduced independently and scaled as maturity grows. This modularity enables incremental adoption without disruption.

Evidence-Based Decision-Making

Estimation and assumption are replaced by validated hypotheses, telemetry, flow metrics, and DORA indicators. Decisions are grounded in data, not guesswork.

Strategy-to-Execution Alignment

Lean Value Trees visualize strategic themes, bets, and initiatives, while OKRs define measurable outcomes. Portfolio Kanban operationalizes flow, ensuring every initiative is traceable to business value.

Team-Centric Execution

Autonomy, ownership, and decentralized decision-making are built into the structure. Teams own outcomes—not tasks—and validate assumptions before committing.

Strategic Adaptability

Quarterly cadences with Slowification windows enable reflection, learning, and strategy refresh. Outcome Mapping and LVT updates ensure priorities evolve with evidence.

Continuous Improvement & Flow Optimization

Lean Kata and Flow Engineering embed systemic learning into delivery. Flow metrics and Portfolio Kanban provide visibility for coaching-led governance.

Sustainable Delivery

Practices like Slowification, hypothesis-driven planning, and coaching-led governance promote resilience, wellbeing, and long-term performance.

In essence:

EmergentOS is not just agile—it is intelligently adaptive. It enables organizations to scale with speed, learn continuously, and deliver outcomes that matter—without sacrificing autonomy, wellbeing, or strategic clarity.

# Appendix: Agility not Agile

EmergentOS is not an Agile methodology. Instead, it is designed to help you and your teams become more agile.

Agility is not a set of rituals or a branded process—it is a mindset and capability. Being “Agile” is not the goal. Agility is the ability to continuously learn, adapt, and deliver better outcomes—for both the organization and the customer.

True agility is achieved by:

- Focusing on customer and business value

- Embracing continuous improvement

- Making decisions based on evidence and learning

- Empowering teams to respond to change with confidence

EmergentOS supports agility by embedding practices that foster alignment, autonomy, flow, and learning—without prescribing a rigid methodology.

## The Four Agile Manifesto Values

- Individuals and interactions over processes and tools

- Working software over comprehensive documentation

- Customer collaboration over contract negotiation

- Responding to change over following a plan

## The 12 principles of The Agile Manifesto

- Our highest priority is to satisfy the customer through early and continuous delivery of valuable software.

- Welcome changing requirements, even late in development. Agile processes harness change for the customer's competitive advantage.

- Deliver working software frequently, from a couple of weeks to a couple of months, with a preference to the shorter timescale.

- Business people and developers must work together daily throughout the project.

- Build projects around motivated individuals. Give them the environment and support they need, and trust them to get the job done.

- The most efficient and effective method of conveying information to and within a development team is face-to-face conversation.

- Working software is the primary measure of progress.

- Agile processes promote sustainable development. The sponsors, developers, and users should be able to maintain a constant pace indefinitely.

- Continuous attention to technical excellence and good design enhances agility.

- Simplicity - the art of maximizing the amount of work not done - is essential.

- The best architectures, requirements, and designs emerge from self-organizing teams.

- At regular intervals, the team reflects on how to become more effective, then tunes and adjusts its behaviour accordingly.

## Mapping EmergentOS to the Agile Principles

| Agile Principle | How EmergentOS Supports It |
| --- | --- |
| 1. Customer satisfaction through early and continuous delivery | Uses quarterly OKRs tied to customer outcomes, CI/CD pipelines, and Kanban to deliver value iteratively. |
| 2. Welcome changing requirements, even late in development | Empirical governance and outcome-driven planning allow teams to adapt goals based on learning and feedback. |
| 3. Deliver working software frequently | CI/CD and DORA metrics encourage frequent, safe deployments. |
| 4. Close, daily cooperation between business people and developers | Stream-aligned teams and shared rituals foster cross-functional collaboration. |
| 5. Build projects around motivated individuals | Team autonomy and coaching playbooks empower individuals and build trust. |
| 6. Face-to-face conversation is the best form of communication | While not prescriptive, the operating system encourages collaborative rituals like retrospectives, OKR planning, and flow reviews. |
| 7. Working software is the primary measure of progress | DORA metrics and telemetry validate delivery impact—not just activity. |
| 8. Sustainable development | The concept of Slowification ensures teams work at a resilient pace, avoiding burnout. |
| 9. Continuous attention to technical excellence and good design | Engineering practices like trunk-based development, automated testing, and infrastructure-as-code are embedded. |
| 10. Simplicity—the art of maximizing the amount of work not done | Kanban and Lean Kata help teams focus on thin slices and reduce waste. |
| 11. Best architectures, requirements, and designs emerge from self-organizing teams | Team Topologies enable decentralized decision-making and scalable autonomy. |
| 12. Regularly reflect and adjust | Quarterly retrospectives, Lean Kata cycles, and flow roadmap reviews embed continuous improvement. |

# Appendix: Why EmergentOS Improves on SAFe® and Similar Models

Many organizations adopt SAFe® (Scaled Agile Framework), or similar scaled Agile frameworks and methodologies, in pursuit of structure, predictability, and alignment at scale—especially when transitioning from traditional waterfall models. SAFe® offers familiar constructs like Program Increments, synchronized cadences, and estimation-driven roadmaps that appeal to leadership seeking control and visibility. However, these same features often become constraints. SAFe’s reliance on predictive scheduling, centralized orchestration, and heavyweight ceremonies can slow delivery, obscure customer outcomes, and disempower teams. Dependencies are managed through planning artifacts rather than team design, and success is frequently measured by feature completion rather than validated impact.

EmergentOS takes a fundamentally different approach. It replaces control with clarity and embeds Value Stream Management as a core principle—ensuring that work is continuously aligned to business outcomes and flow health. Instead of predictive planning, EmergentOS uses quarterly OKRs tied to customer value, supported by Lean Value Trees and Portfolio Kanban for systemic visibility. Dependencies are addressed through Team Topologies, reducing coordination overhead and cognitive load.

Delivery is iterative and empirical, powered by CI/CD pipelines and measured through DORA metrics for engineering performance and Flow Metrics (Velocity, Time, Efficiency, Load, Distribution) for value stream health. These metrics provide leaders with actionable insights into speed, stability, and strategic alignment—replacing anecdotal reporting with evidence-based governance. Continuous improvement is institutionalized through Lean Kata and Flow Engineering, making adaptability a built-in capability rather than an afterthought.

This modular, composable system enables faster learning, greater autonomy, and measurable performance—making it better suited for organizations that need to adapt quickly, deliver continuously, and prove impact in a dynamic digital economy.

## The Problem with Determinism, Predictive Scheduling, and Estimation

Determinism is the belief that outcomes can be predicted with certainty if all inputs and conditions are known. In planning terms, this translates into predictive scheduling and deterministic roadmaps, which assume stability and linear cause-effect relationships.

This mindset works in complicated, predictable domains (like manufacturing) but fails in emergent domains, where uncertainty, complexity, and rapid change dominate. Adaptive delivery thrives on empirical feedback, experimentation, and continuous learning—not rigid forecasts. Deterministic planning creates an illusion of control, locking teams into fixed timelines that collapse under change, while adaptive approaches embrace uncertainty as a source of insight and innovation.

### Estimation Accuracy Is Fundamentally Unreliable

- A systematic review of 28 studies found that traditional software effort estimation techniques—whether algorithmic or expert-based—often suffer from high error rates. Even advanced machine learning models struggle to consistently predict effort with precision37.

- The study highlights that Mean Magnitude of Relative Error (MMRE) and PRED(25)38 metrics frequently show wide variance, indicating that overestimation and underestimation are persistent and systemic issues.

### Different Estimates Create Different Projects

- MIT’s system dynamics research revealed that the act of estimating itself alters project behaviour. Teams adjust scope, staffing, and timelines based on the estimate, not the actual complexity or customer need.39

- This leads to a phenomenon where inaccurate estimates do not just misinform—they actively distort delivery decisions, often resulting in budget overruns and schedule slippage.

### No Universal Estimation Technique Works Across Contexts

- A 2025 literature review published via SpringerLink concluded that no single estimation method applies reliably across all project types or team contexts.40

- Agile techniques like planning poker and story points offer flexibility but still rely on subjective judgment. Hybrid ensemble models show promise but require significant data and calibration.

## Strategic Implications

- Predictive scheduling creates a false sense of certainty, often leading to rigid plans that collapse under change.

- Estimation-heavy planning reinforces output-driven delivery, where success is measured by feature completion rather than customer impact.

- Dependencies are managed through orchestration, not team design—leading to bottlenecks and coordination overhead.

Unlike SAFe®, and similar prescriptive methodologies that apply deterministic approaches, which often relies on centralized planning, estimation rituals, and synchronized PI cycles, EmergentOS decentralizes control and replaces predictability with transparency, adaptability, and evidence. Where certainty is required, empowered product teams make High Integrity Commitments based on validated discovery and data-informed feasibility.

## Why Outcome-Driven, Empirical Delivery Is Better

- Replaces estimation with experimentation (spikes, prototypes, thin slices) to validate feasibility and value.

- Uses flow metrics and DORA indicators to measure actual performance, not predicted effort.

- Aligns teams around customer outcomes and OKRs, not feature roadmaps.

- Manages dependencies through Team Topologies, not synchronized planning.

## Head-to-Head Comparison

| Dimension | EmergentOS | SAFe-like Models |
| --- | --- | --- |
| Planning | Quarterly, outcome-driven | Predictive, estimate-heavy |
| Team Autonomy | High | Low to medium |
| Dependency Management | Topology-based | Planning-based |
| Flow Visibility | Kanban + VSM | PI boards + Gantt |
| Improvement | Lean Kata + telemetry | Retros + governance |
| Engineering Performance | DORA metrics | Often anecdotal |
| Customer Focus | Embedded in OKRs and discovery | Often diluted by feature roadmaps |

# Appendix: Patterns

## Pattern: Big Picture

Context: Teams lack clarity on strategic goals, leading to misaligned efforts.

Problem: Planning is feature-driven. Strategic intent is lost; customer impact is unclear.

Solution: Use Strategic Outcome Mapping to visualize the connection between business objectives, customer outcomes, and team-level OKRs. 
Result: Teams align priorities with measurable outcomes and deliver initiatives that create real business and customer impact.

## Pattern: Coaching Culture

Context: Leadership focuses on control and reporting, limiting team growth.

Problem: Teams lack psychological safety and struggle to improve autonomously.

Solution: Leaders act as coaches, fostering clarity, competence, and continuous learning.

Result: Teams grow in capability, trust increases, and improvement becomes routine.

## Pattern: Deliver Continuously

Context: Releases are infrequent and risky, slowing feedback and learning.

Problem: Manual processes and late integration create bottlenecks and errors.

Solution: Adopt CI/CD to automate builds, tests, and deployments for safe, fast delivery.

Result: Teams release iteratively, validate impact quickly, and reduce risk.

## Pattern: Delivery vs Product Management – Avoiding the Control Trap

Context: Product managers often exhibit project/delivery management behaviours.

Problem: Strategy is diluted; confusion over roles occurs; micromanagement takes place.

Solution: Separate strategic prioritization from flow enablement using EmergentOS.

Result: PMs focus on value; DMs optimize flow and unblock teams; teams operate with clarity.

## Pattern: Flow First

Context: Work piles up, delivery is unpredictable, and improvement is reactive.

Problem: Planning emphasizes scope and dates, not flow health.

Solution: Visualize work with Kanban, apply WIP limits, and use flow metrics to guide decisions.

Result: Work moves predictably, bottlenecks are addressed, and delivery improves.

## Pattern: High Integrity Commitments

Context: Teams are pressured to commit based on estimates and assumptions.

Problem: Speculative commitments lead to missed deadlines and reduced trust.

Solution: Make commitments only after validated discovery and feasibility checks.

Result: Commitments are reliable, evidence-based, and build stakeholder confidence.

## Pattern: Legacy to Learning

Context: Replacing legacy systems with new platforms where work seems predictable.

Problem: Hidden complexity and assumptions undermine deterministic plans.

Solution: Use EmergentOS to validate feasibility, visualize flow, and deliver iteratively.

Result: Migration becomes resilient, outcome-focused, and evidence-driven.

## Pattern: Measure What Matters

Context: Performance is tracked using output metrics or anecdotal feedback.

Problem: Decisions are made without objective data on delivery health.

Solution: Use DORA metrics to measure speed and stability, and guide improvement.

Result: Teams gain actionable insights, improve delivery, and validate engineering practices.

## Pattern: Operate Around Outcomes

Context: Teams are organized around projects and features, not customer value.

Problem: Project-based models create silos and disconnect teams from impact.

Solution: Adopt the Product Operating Model with empowered teams and outcome-driven planning.

Result: Teams own customer outcomes and deliver iteratively with autonomy.

## Pattern: Outcome Over Output

Context: Teams focus on shipping features but struggle to demonstrate customer impact.

Problem: Traditional planning emphasizes output and predictability over learning and adaptability.

Solution: Use OKRs, Kanban, Lean Kata, and validated discovery to shift focus to outcomes.

Result: Teams deliver measurable impact, improve flow, and learn continuously.

## Pattern: Team Topologies

Context: Team structures create bottlenecks and coordination overhead.

Problem: Handoffs and unclear ownership slow delivery and increase cognitive load.

Solution: Apply Team Topologies to structure teams for fast flow and clear ownership.

Result: Delivery accelerates, dependencies are managed, and teams evolve effectively.

## Pattern: Who Does What By How Much

Context: Teams adopt OKRs but struggle to make them outcome-focused and measurable.

Problem: Objectives become vague aspirations; Key Results drift into task lists or vanity metrics.

Solution: Use the formula Who + Does What + By How Much to craft Key Results that reflect real impact, starting with a strong objective and validating alignment.

Result: OKRs become clear, outcome-driven, and actionable, enabling teams to focus on meaningful change and strategic priorities.

## Pattern: Visualize Work

Context: Work is hidden in tools and reports, reducing transparency and trust.

Problem: Teams and leaders lack visibility into progress, blockers, and priorities.

Solution: Use Kanban boards to visualize discovery, delivery, and improvement work.

Result: Transparency improves, blockers are surfaced, and alignment increases.

# Glossary

API: Application Programming Interface

CD: Continuous Delivery

CI: Continuous Integration

DORA: DevOps Research and Assessment

EOS: EmergentOS

LVT: Lean Value Tree

KR: Key Result

KTLO: Keeping The Light On

MTTR: Mean Time to Recovery

OKR: Objectives and Key Results

PI: Program Increment

VSM: Value Stream Management

WIP: Work In Progress

Smart, J. (2020). SOONER SAFER HAPPIER : patterns and antipatterns for organizational agility. S.L.: It Revolution Pr.

Doerr, J.E. (2018). Measure what matters : OKRs, the simple idea that drives 10x growth. Great Britain Portfolio.

Skelton, M. and Pais, M. (2019). Team topologies: organizing business and technology teams for fast flow. Portland, Oregon: It Revolution.

Jez Humble, Molesky, J. and O’reilly, B. (2017). Lean enterprise. Heidelberg O’reilly.

Fowler, M. (2024). Continuous Integration. [online] martinfowler.com. Available at: https://martinfowler.com/articles/continuousIntegration.html.

Humble, J. and Farley, D. (2011). Continuous Delivery: Reliable Software Releases through Build, Test, and Deployment Automation. Upper Saddle River, Nj: Addison-Wesley.

Dora.dev. (2024). DORA | Research. [online] Available at: https://dora.dev/research/.

Mik Kersten (2018). Project to product : how to survive and thrive in the age of digital disruption with the flow framework. Portland, Or: It Revolution.

Linda Rising Ph.D and Lynn, M. (2004). Fearless Change. Pearson Education.

Cagan, M. (2018). Inspired: How to create tech products customers love. Hoboken: Wiley.

Cagan, M. (2020). EMPOWERED. John Wiley & Sons.

Cagan, M. (2024). Transformed. John Wiley & Sons.

Kim, G. and Spear, S.J. (2023). Wiring the Winning Organization. IT Revolution.

Silicon Valley Product Group. (n.d.). Marty Cagan. [online] Available at: https://www.svpg.com/team/marty-cagan/.

The opposite being roof shot goal, one which lacks ambition and is easy to achieve.

Doerr, J.E. (2018). Measure what matters: OKRs, the simple idea that drives 10x growth. Great Britain Portfolio.

The word Kata comes from Japanese martial arts, where it refers to a structured form or pattern of movement practiced repeatedly to build skill, discipline, and mastery. A kata is not just a routine—it’s a codified sequence of steps that teaches foundational principles through repetition and refinement.

Dora.dev. (2021). DORA | DORA’s software delivery metrics: the four keys. [online] Available at: https://dora.dev/guides/dora-metrics-four-keys/.

Forsgren, N., Humble, J. and Kim, G. (2018). Accelerate : the science behind DevOps : building and scaling high performing technology organizations. Portland, Oregon: It Revolution.

Understanding Flow Distribution – Getting Your Priorities Straight. https://blog.planview.com/flow-distribution/

Intentbasedleadership.com. (2025). Intent Based Leadership. [online] Available at: https://www.intentbasedleadership.com/ [Accessed 2 Oct. 2025].

Beck, K. (2001). Manifesto for Agile Software Development. [online] agilemanifesto.org. Available at: https://agilemanifesto.org.

Beck, K. (2001). Principles behind the Agile Manifesto. [online] Agilemanifesto.org. Available at: https://agilemanifesto.org/principles.html.

https://www.agilefever.com/the-ultimate-guide-to-pros-and-cons-safe-framework/

https://www.mdpi.com/2078-2489/15/10/592

https://dev.to/tracywhodoesnot/why-safe-fails-a-critical-analysis-of-scaled-agile-frameworks-and-better-alternatives-o9k

https://projectmanagementacademy.net/resources/blog/common-problems-with-safe/

Ries, E. (2011). The Lean Startup. London: Portfolio Penguin.

Doerr, J.E. (2018). Measure what matters : OKRs, the simple idea that drives 10x growth. Great Britain Portfolio.

Cagan, M. (2020). EMPOWERED. John Wiley & Sons.

Pereira, S. and Davis, A. (2024). Flow Engineering. IT Revolution.

Fowler, M. (2024). Continuous Integration. [online] martinfowler.com. Available at: https://martinfowler.com/articles/continuousIntegration.html.

Humble, J. and Farley, D. (2011). Continuous Delivery: Reliable Software Releases through Build, Test, and Deployment Automation. Upper Saddle River, Nj: Addison-Wesley.

Highsmith, J., Luu, L. and Robinson, D. (2019). EDGE. Addison-Wesley Professional.

Highsmith, J., Luu, L. and Robinson, D. (2019). EDGE. Addison-Wesley Professional.

Kersten, M. (2018). Project to product : how to survive and thrive in the age of digital disruption with the flow framework. Portland, OR: IT Revolution Press.

Nike. (1988). Just Do It [Slogan]. Nike, Inc.

Smart, J. (2020). SOONER SAFER HAPPIER : patterns and antipatterns for organizational agility. S.L.: It Revolution Pr.

Smart, J. (2020). SOONER SAFER HAPPIER : patterns and antipatterns for organizational agility. S.L.: It Revolution Pr.

Innovation Accounting: Ries, E. (2011). The Lean Startup. London: Portfolio Penguin.

Ries, E. (2017). The startup way : how modern companies use entrepreneurial management to transform culture and drive long-term growth. New York: Currency.

Smart, J. (2020). SOONER SAFER HAPPIER : patterns and antipatterns for organizational agility. S.L.: It Revolution Pr.

Highsmith, J., Luu, L. and Robinson, D. (2019). EDGE. Addison-Wesley Professional.

Cagan, M. (2018). Inspired: How to create tech products customers love. Hoboken: Wiley.

Highsmith, J., Luu, L. and Robinson, D. (2019). EDGE. Addison-Wesley Professional.

Kim, G. and Spear, S.J. (2023). Wiring the Winning Organization. IT Revolution.

In his books The Lean Startup and The Startup Way, Eric Ries describes these as Leap of Faith Assumptions - the critical, unproven beliefs that must be true for a product, initiative, or strategy to succeed—but which currently lack evidence.

Smart, J. (2020). SOONER SAFER HAPPIER : patterns and antipatterns for organizational agility. S.L.: It Revolution Pr.

”Think Big, Start Small, Learn Fast”: O’reilly, B. (2019). Unlearn : let go of past success to achieve extraordinary results. New York: Mcgraw-Hill Education.

Better Value, Sooner, Safer, Happier. Smart, J. (2020). SOONER SAFER HAPPIER : patterns and antipatterns for organizational agility. S.L.: It Revolution Pr.

In Jonathan Smart’s BVSSH (Smart, J. (2020). SOONER SAFER HAPPIER : patterns and antipatterns for organizational agility. S.L.: It Revolution Pr.), he refers to an equivalent triumvirate of roles: the Value Outcome Lead, the Team Outcome Lead, and Architecture Outcome Lead, who together play a similar servant leadership role.

Highsmith, J., Luu, L. and Robinson, D. (2019). EDGE. Addison-Wesley Professional.

Smart, J. (2020). SOONER SAFER HAPPIER : patterns and antipatterns for organizational agility. S.L.: It Revolution Pr.

Seiden, J. and Gothelf, J. (2024). Who Does What By How Much? Sense & Respond Press.

Seiden, J. and Gothelf, J. (2024). Who Does What By How Much? Sense & Respond Press.

Gothelf, J. and Seiden, J. (2016). Lean UX : designing great products with agile teams. Beijing: O’reilly.